## Executive Dashboard
Google 90-Day Mountain Plan — Enterprise AI Product & Transformation Leader
Strategic decision | Definition |  | Readiness dimension | Weight | Target | Actual | Weighted score | Signal | Evidence source
Primary Google contribution | Identify expensive enterprise problems, convert them into repeatable Google-centered AI products, and win CXO adoption. |  | Flagship product quality | 20% | 90 | 0 | 0 | Gap | Product Portfolio
Primary role hypothesis | Pursuit AI Lead / AI Transformation Lead / Industry Solutions or Value Creation Lead. |  | External customer validation | 15% | 80 | 0 | 0 | Gap | Design Partner Program
Concrete India parallel route | Consulting Account Lead or equivalent senior Google Cloud transformation role. |  | Google-specific commercial thesis | 12% | 85 | 0 | 0 | Gap | Google Commercial Value
Compensation condition | Target role must plausibly support ₹1 crore+ annual total compensation; do not enter through a clearly under-level role. |  | Historical product evidence | 10% | 90 | 0 | 0 | Gap | Historical Portfolio
90-day founder capacity | 180 hours: two high-intensity hours every day. |  | Technical fluency and architecture defence | 10% | 75 | 0 | 0 | Gap | 90-Day Program
Flagship outcome | Decision360 public beta with validated buyer workflows and credible technical, economic and governance evidence. |  | Original thought leadership | 10% | 80 | 0 | 0 | Gap | Launch & Prominence
Original market contribution | Decision Agent Benchmark public alpha and position paper. |  | Competitive differentiation | 8% | 80 | 0 | 0 | Gap | Competitive Landscape
Supporting proof | Transformation Mapper prototype; Commerce Growth vertical demonstration. |  | Senior role and compensation calibration | 8% | 100 | 0 | 0 | Gap | North Star & Role
Readiness target | Earn internal sponsorship for a named senior role—not merely submit applications. |  | IP / clean-room confidence | 4% | 100 | 0 | 0 | Gap | IP Clean-Room Review
Non-negotiable | External validation, clean-room IP review, Google commercial logic and personal decision evidence. |  | Internal sponsorship | 3% | 100 | 0 | 0 | Gap | Google Launch Package
Bulletproof gate | Due day | Pass condition | Program score | Formula | Current | Decision
G1 Role truth | 10 | Two insiders independently validate role family, seniority and likely compensation path. | Weighted readiness | Sum of weighted scores | 0 | Delay formal launch
G2 Problem truth | 20 | At least six relevant practitioners confirm the problem, buyer and current failure. | Launch rule | ≥80 strong launch; 70–79 selective; <70 delay formal launch | 0 | Delay formal launch
G3 Product truth | 45 | Decision360 completes five workflows and at least three reviewers use it without live guidance.
G4 Commercial truth | 60 | Google-specific land-and-expand economics and competitive advantage survive expert challenge.
G5 Evidence truth | 75 | Evaluation, security, IP and decision log support every public claim.
G6 Sponsorship truth | 85 | A relevant Google insider agrees to sponsor an introduction to a named team or role.
G7 Public launch | 90 | Flagship beta, benchmark alpha, portfolio site, paper, demo and launch sequence are public-ready.

## North Star & Role
Priority | Role family | Why this is your contribution | Must prove | Disqualifier | Internal validation required | Compensation question | Status | Evidence | Decision
1 | Pursuit AI Lead / AI Transformation Lead | Own executive problem discovery, AI transformation strategy, repeatable offers and commercial pursuit. | Google Cloud fluency; AI services roadmap; proposal/pursuit ownership; repeatable assets. | Profile appears as generic analytics consultant or idea generator. | Current team existence, India/region scope, level, hiring bar and sponsor. | Can this role at the calibrated level exceed ₹1 crore TC in India? | Not Started
2 | Industry Solutions / Value Creation Lead | Turn Google technology into measurable CPG, retail and manufacturing outcomes. | Reusable industry solution; economic model; CXO narrative; partner/field usability. | No proof of scale beyond one bespoke client. | Which team owns CPG/manufacturing industry productization? | What level maps to regional or portfolio ownership? | Not Started
3 | Consulting Account Lead | Orchestrate strategic transformation journeys and trusted-advisor relationships. | Cloud/digital implementation leadership; executive governance; delivery orchestration. | Weak evidence of cloud transformation delivery or commercial accountability. | Role level, account size, quota/pipeline expectations and India compensation. | Is this a senior enough route without resetting scope? | Not Started
4 | Senior Outbound Product / Industry Product Strategy | Bring customer problems into product strategy, launch and adoption. | Roadmap ownership; prioritization; product launch; adoption and market evidence. | Only prototypes, no product discipline or adoption proof. | Whether industry/outbound PM roles value non-traditional PM history. | Can product scope support senior level? | Not Started
5 | Practice Customer Engineer — Applied AI | Technical-commercial adjacent route; useful only if senior strategic scope. | Architecture defence, workshops, prototypes and Google Cloud credibility. | Role is too presales-technical or under-level for your objective. | Whether role allows industry solution creation and compensation target. | Does advanced CE scope cross ₹1 crore TC? | Not Started
Calibration question | Friend 1 answer | Insider 2 answer | Recruiter/HM answer | Agreement? | Risk | Action | Due day
Which team would most value someone who discovers enterprise problems and productizes repeatable AI solutions? |  |  |  | No/Unknown | High | Obtain two independent answers | 7
Which level is realistic given 17+ years but limited formal Google Cloud tenure? |  |  |  | No/Unknown | Critical | Do not apply until calibrated | 10
What evidence would make an internal sponsor personally comfortable introducing me? |  |  |  | No/Unknown | High | Convert answer into launch gates | 10
How much cloud architecture depth is tested for transformation/pursuit roles? |  |  |  | No/Unknown | High | Create fluency syllabus | 10
Which exact India or APAC roles can plausibly cross ₹1 crore TC? |  |  |  | No/Unknown | Critical | Reject structurally under-level paths | 14
What distinguishes people who succeed from consultants who fail after joining? |  |  |  | No/Unknown | High | Add operating-model evidence | 14
Current official evidence | What it means | URL | Plan implication
Pursuit AI Lead role emphasizes executive problem discovery, holistic AI transformation strategy, repeatable solutions and services pursuits. | Directionally closest role family, but the current listing found is US-based and mid-level. | https://www.google.com/about/careers/applications/jobs/results/89911139634160326-pursuit-ai-lead/ | Use as contribution archetype, not assumed India vacancy or level.
Consulting Account Lead in Bengaluru/Mumbai is marked Advanced and asks for 10 years consulting/IT services plus cloud/digital implementation experience. | Concrete current India senior route, but cloud implementation evidence is mandatory. | https://www.google.com/about/careers/applications/jobs/results/137289443466715846-consulting-account-lead/ | Maintain as parallel role and strengthen implementation story.
Google ADK supports tools, workflow/multi-agent orchestration, evaluation and deployment to Runtime, Cloud Run or GKE. | The products should use Google platform capabilities rather than recreate them. | https://docs.cloud.google.com/gemini-enterprise-agent-platform/build/adk | Focus differentiation on domain workflow, economics and decision quality.
Google agent evaluation already covers final responses, task success, safety, trajectories, synthetic scenarios and monitoring. | The benchmark must extend—not duplicate—Google evaluation. | https://docs.cloud.google.com/gemini-enterprise-agent-platform/optimize/evaluation/agent-evaluation | Narrow benchmark to regret, calibration, realized value, adoption and governance.

## 90-Day Program
Phase | Days | Founder hours | Primary outcome | Decision360 | Agent Benchmark | Transformation Mapper | Commerce Growth | External proof | Google proof | Hard gate | Failure response | Status
Phase 1 — Truth before build | 1–14 | 28 | Role, buyer, problem, IP and competitive hypotheses validated. | PRD and five buyer workflows | Metric thesis and novelty boundary | Problem and scoring thesis | Market thesis only | 6 interviews | 2 insider calibrations | G1 and G2 | Rewrite scope; no full build | Not Started
Phase 2 — Shared spine + flagship | 15–35 | 42 | Shared platform and Decision360 thin vertical slice. | Data, risk, scenario, recommendation, approval | Task/trace schema | Evidence ingestion spike | Catalog data spike | 3 repeat reviewers | Architecture review | Technical spine works | Shift 80% to flagship | Not Started
Phase 3 — Flagship public beta | 36–50 | 30 | Decision360 works without live handholding. | Five workflows, evaluation and value case | Metric plugins alpha | Thin extraction prototype | Vertical specification | 3 unguided tests | Google/architect review | G3 | Cut features until reliable | Not Started
Phase 4 — Originality and portfolio | 51–65 | 30 | Benchmark alpha plus Transformation Mapper prototype. | Polish and pilot pack | 40-task benchmark alpha | Evidence→opportunity→score demo | Athlete nutrition demo | 4 expert reviews | Commercial challenge session | G4 | Drop Commerce extras first | Not Started
Phase 5 — Evidence and senior narrative | 66–78 | 26 | Competitive, commercial, historical and technical evidence is complete. | Case study and defensibility | Paper and findings | Case study | Market paper section | 3 second-round reviewers | Role sponsor review | G5 | Delay public claims | Not Started
Phase 6 — Sponsorship and launch | 79–90 | 24 | Public launch package and named-role sponsorship. | Public beta | Public alpha | Prototype | Vertical demo | Testimonials/quotes where permitted | Named-team introduction | G6 and G7 | Selective launch only | Not Started
Technical fluency domain | Required level | Proof | Due day | Status | Explain in 5 min? | Can challenge engineer? | Hands-on exercise | Failure mode | Remediation
Google Cloud data and agent architecture | Architecturally fluent | End-to-end diagrams and five ADRs | 35 | Not Started | No | No | Deploy one agent workflow | Cannot defend stack choices | Daily architecture drills
BigQuery, IAM, Cloud Run/Agent Runtime | Working fluency | Secure demo and cost model | 40 | Not Started | No | No | Run/deploy/debug core service | Looks like deck-only leader | One hands-on lab per service
ADK tools, workflows and evaluation | Working fluency | Tool agent and benchmark runner | 55 | Not Started | No | No | Implement and test one tool flow | Cannot explain agent failures | Review traces and failure taxonomy
RAG, evidence, text-to-SQL and safety | Architecturally fluent | Decision360 evidence and safety tests | 50 | Not Started | No | No | Create ten adversarial cases | Generic AI claims | Red-team weekly
Hybrid Azure-heavy enterprise integration | Strategic fluency | Integration pattern and migration-neutral pitch | 60 | Not Started | No | No | Draw Azure+GCP coexistence architecture | Sounds anti-Azure or unrealistic | Competitor/interoperability review
Cost, latency, scale and operations | Strategic fluency | Unit economics and p95 telemetry | 65 | Not Started | No | No | Estimate workflow cost and bottlenecks | No credible production story | Instrument all demos

## Daily 2-Hour Plan
Day | Week | Date | Phase | Primary focus | Hour 1 — Rick | Hour 2 — Rick | Codex overnight handoff | Required evidence | Gate contribution | Status | Hours | Blocker / learning
1 | 1 | 2026-07-18 | Truth before build | Role calibration | Prepare targeted insider questions and exact contribution thesis. | Conduct/review conversation; update role and level assumptions. | Update role dossier and decisions_needed.md | Written answer or scheduled conversation | G1 | Not Started | 0
2 | 1 | 2026-07-19 | Truth before build | Design partner discovery | Prepare buyer-specific interview and current-state hypothesis. | Conduct interview or synthesize evidence into PRD changes. | Update interview evidence and backlog deltas | Interview notes plus changed assumption | G2 | Not Started | 0
3 | 1 | 2026-07-20 | Truth before build | Competitive truth | Compare one competitor against the product workflow, economics and lock-in. | Write why the product should or should not be Google-centered. | Update competitor matrix and kill criteria | Defensible differentiation statement | G2 | Not Started | 0
4 | 1 | 2026-07-21 | Truth before build | IP clean room | Review one historic product/feature for ownership and safe abstraction. | Write clean-room rule and excluded elements. | Update IP checklist and public wording | Signed-off exclusion list | G5 | Not Started | 0
5 | 1 | 2026-07-22 | Truth before build | Role calibration | Prepare targeted insider questions and exact contribution thesis. | Conduct/review conversation; update role and level assumptions. | Update role dossier and decisions_needed.md | Written answer or scheduled conversation | G1 | Not Started | 0
6 | 1 | 2026-07-23 | Truth before build | Design partner discovery | Prepare buyer-specific interview and current-state hypothesis. | Conduct interview or synthesize evidence into PRD changes. | Update interview evidence and backlog deltas | Interview notes plus changed assumption | G2 | Not Started | 0
7 | 1 | 2026-07-24 | Truth before build | Competitive truth | Compare one competitor against the product workflow, economics and lock-in. | Write why the product should or should not be Google-centered. | Update competitor matrix and kill criteria | Defensible differentiation statement | G2 | Not Started | 0
8 | 2 | 2026-07-25 | Truth before build | IP clean room | Review one historic product/feature for ownership and safe abstraction. | Write clean-room rule and excluded elements. | Update IP checklist and public wording | Signed-off exclusion list | G5 | Not Started | 0
9 | 2 | 2026-07-26 | Truth before build | Role calibration | Prepare targeted insider questions and exact contribution thesis. | Conduct/review conversation; update role and level assumptions. | Update role dossier and decisions_needed.md | Written answer or scheduled conversation | G1 | Not Started | 0
10 | 2 | 2026-07-27 | Truth before build | Design partner discovery | Prepare buyer-specific interview and current-state hypothesis. | Conduct interview or synthesize evidence into PRD changes. | Update interview evidence and backlog deltas | Interview notes plus changed assumption | G2 | Not Started | 0
11 | 2 | 2026-07-28 | Truth before build | Competitive truth | Compare one competitor against the product workflow, economics and lock-in. | Write why the product should or should not be Google-centered. | Update competitor matrix and kill criteria | Defensible differentiation statement | G2 | Not Started | 0
12 | 2 | 2026-07-29 | Truth before build | IP clean room | Review one historic product/feature for ownership and safe abstraction. | Write clean-room rule and excluded elements. | Update IP checklist and public wording | Signed-off exclusion list | G5 | Not Started | 0
13 | 2 | 2026-07-30 | Truth before build | Role calibration | Prepare targeted insider questions and exact contribution thesis. | Conduct/review conversation; update role and level assumptions. | Update role dossier and decisions_needed.md | Written answer or scheduled conversation | G1 | Not Started | 0
14 | 2 | 2026-07-31 | Truth before build | Design partner discovery | Prepare buyer-specific interview and current-state hypothesis. | Conduct interview or synthesize evidence into PRD changes. | Update interview evidence and backlog deltas | Interview notes plus changed assumption | G2 | Not Started | 0
15 | 3 | 2026-08-01 | Shared spine + flagship | External review | Prepare a focused review script around one risk. | Run review or incorporate feedback into backlog. | Create change request with evidence | Reviewer feedback and product change | G3 | Not Started | 0
16 | 3 | 2026-08-02 | Shared spine + flagship | Decision360 flagship | Specify one end-to-end user decision and acceptance threshold. | Review/test Codex output; reject generic or untraceable behavior. | Implement next vertical slice with tests | Working workflow and decision record | G3 | Not Started | 0
17 | 3 | 2026-08-03 | Shared spine + flagship | Technical fluency | Study one architecture topic from the actual product. | Explain it aloud and challenge one alternative. | Create ADR, diagram and lab evidence | 5-minute defence plus artifact | G3 | Not Started | 0
18 | 3 | 2026-08-04 | Shared spine + flagship | External review | Prepare a focused review script around one risk. | Run review or incorporate feedback into backlog. | Create change request with evidence | Reviewer feedback and product change | G3 | Not Started | 0
19 | 3 | 2026-08-05 | Shared spine + flagship | Decision360 flagship | Specify one end-to-end user decision and acceptance threshold. | Review/test Codex output; reject generic or untraceable behavior. | Implement next vertical slice with tests | Working workflow and decision record | G3 | Not Started | 0
20 | 3 | 2026-08-06 | Shared spine + flagship | Technical fluency | Study one architecture topic from the actual product. | Explain it aloud and challenge one alternative. | Create ADR, diagram and lab evidence | 5-minute defence plus artifact | G3 | Not Started | 0
21 | 3 | 2026-08-07 | Shared spine + flagship | External review | Prepare a focused review script around one risk. | Run review or incorporate feedback into backlog. | Create change request with evidence | Reviewer feedback and product change | G3 | Not Started | 0
22 | 4 | 2026-08-08 | Shared spine + flagship | Decision360 flagship | Specify one end-to-end user decision and acceptance threshold. | Review/test Codex output; reject generic or untraceable behavior. | Implement next vertical slice with tests | Working workflow and decision record | G3 | Not Started | 0
23 | 4 | 2026-08-09 | Shared spine + flagship | Technical fluency | Study one architecture topic from the actual product. | Explain it aloud and challenge one alternative. | Create ADR, diagram and lab evidence | 5-minute defence plus artifact | G3 | Not Started | 0
24 | 4 | 2026-08-10 | Shared spine + flagship | External review | Prepare a focused review script around one risk. | Run review or incorporate feedback into backlog. | Create change request with evidence | Reviewer feedback and product change | G3 | Not Started | 0
25 | 4 | 2026-08-11 | Shared spine + flagship | Decision360 flagship | Specify one end-to-end user decision and acceptance threshold. | Review/test Codex output; reject generic or untraceable behavior. | Implement next vertical slice with tests | Working workflow and decision record | G3 | Not Started | 0
26 | 4 | 2026-08-12 | Shared spine + flagship | Technical fluency | Study one architecture topic from the actual product. | Explain it aloud and challenge one alternative. | Create ADR, diagram and lab evidence | 5-minute defence plus artifact | G3 | Not Started | 0
27 | 4 | 2026-08-13 | Shared spine + flagship | External review | Prepare a focused review script around one risk. | Run review or incorporate feedback into backlog. | Create change request with evidence | Reviewer feedback and product change | G3 | Not Started | 0
28 | 4 | 2026-08-14 | Shared spine + flagship | Decision360 flagship | Specify one end-to-end user decision and acceptance threshold. | Review/test Codex output; reject generic or untraceable behavior. | Implement next vertical slice with tests | Working workflow and decision record | G3 | Not Started | 0
29 | 5 | 2026-08-15 | Shared spine + flagship | Technical fluency | Study one architecture topic from the actual product. | Explain it aloud and challenge one alternative. | Create ADR, diagram and lab evidence | 5-minute defence plus artifact | G3 | Not Started | 0
30 | 5 | 2026-08-16 | Shared spine + flagship | External review | Prepare a focused review script around one risk. | Run review or incorporate feedback into backlog. | Create change request with evidence | Reviewer feedback and product change | G3 | Not Started | 0
31 | 5 | 2026-08-17 | Shared spine + flagship | Decision360 flagship | Specify one end-to-end user decision and acceptance threshold. | Review/test Codex output; reject generic or untraceable behavior. | Implement next vertical slice with tests | Working workflow and decision record | G3 | Not Started | 0
32 | 5 | 2026-08-18 | Shared spine + flagship | Technical fluency | Study one architecture topic from the actual product. | Explain it aloud and challenge one alternative. | Create ADR, diagram and lab evidence | 5-minute defence plus artifact | G3 | Not Started | 0
33 | 5 | 2026-08-19 | Shared spine + flagship | External review | Prepare a focused review script around one risk. | Run review or incorporate feedback into backlog. | Create change request with evidence | Reviewer feedback and product change | G3 | Not Started | 0
34 | 5 | 2026-08-20 | Shared spine + flagship | Decision360 flagship | Specify one end-to-end user decision and acceptance threshold. | Review/test Codex output; reject generic or untraceable behavior. | Implement next vertical slice with tests | Working workflow and decision record | G3 | Not Started | 0
35 | 5 | 2026-08-21 | Shared spine + flagship | Technical fluency | Study one architecture topic from the actual product. | Explain it aloud and challenge one alternative. | Create ADR, diagram and lab evidence | 5-minute defence plus artifact | G3 | Not Started | 0
36 | 6 | 2026-08-22 | Flagship public beta | Commercial proof | Quantify customer outcome and Google consumption path. | Stress-test assumptions against Azure/specialist alternatives. | Update unit economics and land-expand model | Transparent assumptions and sensitivity | G4 | Not Started | 0
37 | 6 | 2026-08-23 | Flagship public beta | Decision360 beta | Run one full workflow as a buyer/user, without developer shortcuts. | Inspect failures, metrics and business logic; approve or reject release. | Fix top issue and expand regression suite | Passed workflow and failure report | G3 | Not Started | 0
38 | 6 | 2026-08-24 | Flagship public beta | Commercial proof | Quantify customer outcome and Google consumption path. | Stress-test assumptions against Azure/specialist alternatives. | Update unit economics and land-expand model | Transparent assumptions and sensitivity | G4 | Not Started | 0
39 | 6 | 2026-08-25 | Flagship public beta | Decision360 beta | Run one full workflow as a buyer/user, without developer shortcuts. | Inspect failures, metrics and business logic; approve or reject release. | Fix top issue and expand regression suite | Passed workflow and failure report | G3 | Not Started | 0
40 | 6 | 2026-08-26 | Flagship public beta | Commercial proof | Quantify customer outcome and Google consumption path. | Stress-test assumptions against Azure/specialist alternatives. | Update unit economics and land-expand model | Transparent assumptions and sensitivity | G4 | Not Started | 0
41 | 6 | 2026-08-27 | Flagship public beta | Decision360 beta | Run one full workflow as a buyer/user, without developer shortcuts. | Inspect failures, metrics and business logic; approve or reject release. | Fix top issue and expand regression suite | Passed workflow and failure report | G3 | Not Started | 0
42 | 6 | 2026-08-28 | Flagship public beta | Commercial proof | Quantify customer outcome and Google consumption path. | Stress-test assumptions against Azure/specialist alternatives. | Update unit economics and land-expand model | Transparent assumptions and sensitivity | G4 | Not Started | 0
43 | 7 | 2026-08-29 | Flagship public beta | Decision360 beta | Run one full workflow as a buyer/user, without developer shortcuts. | Inspect failures, metrics and business logic; approve or reject release. | Fix top issue and expand regression suite | Passed workflow and failure report | G3 | Not Started | 0
44 | 7 | 2026-08-30 | Flagship public beta | Commercial proof | Quantify customer outcome and Google consumption path. | Stress-test assumptions against Azure/specialist alternatives. | Update unit economics and land-expand model | Transparent assumptions and sensitivity | G4 | Not Started | 0
45 | 7 | 2026-08-31 | Flagship public beta | Decision360 beta | Run one full workflow as a buyer/user, without developer shortcuts. | Inspect failures, metrics and business logic; approve or reject release. | Fix top issue and expand regression suite | Passed workflow and failure report | G3 | Not Started | 0
46 | 7 | 2026-09-01 | Flagship public beta | Commercial proof | Quantify customer outcome and Google consumption path. | Stress-test assumptions against Azure/specialist alternatives. | Update unit economics and land-expand model | Transparent assumptions and sensitivity | G4 | Not Started | 0
47 | 7 | 2026-09-02 | Flagship public beta | Decision360 beta | Run one full workflow as a buyer/user, without developer shortcuts. | Inspect failures, metrics and business logic; approve or reject release. | Fix top issue and expand regression suite | Passed workflow and failure report | G3 | Not Started | 0
48 | 7 | 2026-09-03 | Flagship public beta | Commercial proof | Quantify customer outcome and Google consumption path. | Stress-test assumptions against Azure/specialist alternatives. | Update unit economics and land-expand model | Transparent assumptions and sensitivity | G4 | Not Started | 0
49 | 7 | 2026-09-04 | Flagship public beta | Decision360 beta | Run one full workflow as a buyer/user, without developer shortcuts. | Inspect failures, metrics and business logic; approve or reject release. | Fix top issue and expand regression suite | Passed workflow and failure report | G3 | Not Started | 0
50 | 8 | 2026-09-05 | Flagship public beta | Commercial proof | Quantify customer outcome and Google consumption path. | Stress-test assumptions against Azure/specialist alternatives. | Update unit economics and land-expand model | Transparent assumptions and sensitivity | G4 | Not Started | 0
51 | 8 | 2026-09-06 | Originality + portfolio | Commerce vertical | Build athlete-nutrition category problem, with safety boundaries. | Review business buyer, data and non-medical product logic. | Implement vertical demo/specification | Market-ready vertical story | G4 | Not Started | 0
52 | 8 | 2026-09-07 | Originality + portfolio | Agent Benchmark | Define or run one decision-quality benchmark case. | Review whether metric adds value beyond Google technical evaluation. | Implement metric/task/report and tests | Reproducible benchmark evidence | G4 | Not Started | 0
53 | 8 | 2026-09-08 | Originality + portfolio | Transformation Mapper | Specify or test evidence-to-opportunity workflow. | Challenge unsupported ideas and scoring assumptions. | Implement thin slice and baseline comparison | Traceable opportunity case | G4 | Not Started | 0
54 | 8 | 2026-09-09 | Originality + portfolio | Commerce vertical | Build athlete-nutrition category problem, with safety boundaries. | Review business buyer, data and non-medical product logic. | Implement vertical demo/specification | Market-ready vertical story | G4 | Not Started | 0
55 | 8 | 2026-09-10 | Originality + portfolio | Agent Benchmark | Define or run one decision-quality benchmark case. | Review whether metric adds value beyond Google technical evaluation. | Implement metric/task/report and tests | Reproducible benchmark evidence | G4 | Not Started | 0
56 | 8 | 2026-09-11 | Originality + portfolio | Transformation Mapper | Specify or test evidence-to-opportunity workflow. | Challenge unsupported ideas and scoring assumptions. | Implement thin slice and baseline comparison | Traceable opportunity case | G4 | Not Started | 0
57 | 9 | 2026-09-12 | Originality + portfolio | Commerce vertical | Build athlete-nutrition category problem, with safety boundaries. | Review business buyer, data and non-medical product logic. | Implement vertical demo/specification | Market-ready vertical story | G4 | Not Started | 0
58 | 9 | 2026-09-13 | Originality + portfolio | Agent Benchmark | Define or run one decision-quality benchmark case. | Review whether metric adds value beyond Google technical evaluation. | Implement metric/task/report and tests | Reproducible benchmark evidence | G4 | Not Started | 0
59 | 9 | 2026-09-14 | Originality + portfolio | Transformation Mapper | Specify or test evidence-to-opportunity workflow. | Challenge unsupported ideas and scoring assumptions. | Implement thin slice and baseline comparison | Traceable opportunity case | G4 | Not Started | 0
60 | 9 | 2026-09-15 | Originality + portfolio | Commerce vertical | Build athlete-nutrition category problem, with safety boundaries. | Review business buyer, data and non-medical product logic. | Implement vertical demo/specification | Market-ready vertical story | G4 | Not Started | 0
61 | 9 | 2026-09-16 | Originality + portfolio | Agent Benchmark | Define or run one decision-quality benchmark case. | Review whether metric adds value beyond Google technical evaluation. | Implement metric/task/report and tests | Reproducible benchmark evidence | G4 | Not Started | 0
62 | 9 | 2026-09-17 | Originality + portfolio | Transformation Mapper | Specify or test evidence-to-opportunity workflow. | Challenge unsupported ideas and scoring assumptions. | Implement thin slice and baseline comparison | Traceable opportunity case | G4 | Not Started | 0
63 | 9 | 2026-09-18 | Originality + portfolio | Commerce vertical | Build athlete-nutrition category problem, with safety boundaries. | Review business buyer, data and non-medical product logic. | Implement vertical demo/specification | Market-ready vertical story | G4 | Not Started | 0
64 | 10 | 2026-09-19 | Originality + portfolio | Agent Benchmark | Define or run one decision-quality benchmark case. | Review whether metric adds value beyond Google technical evaluation. | Implement metric/task/report and tests | Reproducible benchmark evidence | G4 | Not Started | 0
65 | 10 | 2026-09-20 | Originality + portfolio | Transformation Mapper | Specify or test evidence-to-opportunity workflow. | Challenge unsupported ideas and scoring assumptions. | Implement thin slice and baseline comparison | Traceable opportunity case | G4 | Not Started | 0
66 | 10 | 2026-09-21 | Evidence + senior narrative | Senior narrative | Practice the 15-minute Google thesis and three probing questions. | Record, critique and rewrite weak sections. | Update talk track and evidence links | Interview-ready answer | G5 | Not Started | 0
67 | 10 | 2026-09-22 | Evidence + senior narrative | Evidence hardening | Run adversarial, safety, data-quality or baseline comparison. | Write failure analysis and decide public claim limits. | Fix or document limitation | Evaluation report entry | G5 | Not Started | 0
68 | 10 | 2026-09-23 | Evidence + senior narrative | Historical portfolio | Convert one real product into a safe, quantified case study. | Verify personal role, reusable logic, adoption and confidentiality. | Update portfolio site content | Credible historical proof | G5 | Not Started | 0
69 | 10 | 2026-09-24 | Evidence + senior narrative | Senior narrative | Practice the 15-minute Google thesis and three probing questions. | Record, critique and rewrite weak sections. | Update talk track and evidence links | Interview-ready answer | G5 | Not Started | 0
70 | 10 | 2026-09-25 | Evidence + senior narrative | Evidence hardening | Run adversarial, safety, data-quality or baseline comparison. | Write failure analysis and decide public claim limits. | Fix or document limitation | Evaluation report entry | G5 | Not Started | 0
71 | 11 | 2026-09-26 | Evidence + senior narrative | Historical portfolio | Convert one real product into a safe, quantified case study. | Verify personal role, reusable logic, adoption and confidentiality. | Update portfolio site content | Credible historical proof | G5 | Not Started | 0
72 | 11 | 2026-09-27 | Evidence + senior narrative | Senior narrative | Practice the 15-minute Google thesis and three probing questions. | Record, critique and rewrite weak sections. | Update talk track and evidence links | Interview-ready answer | G5 | Not Started | 0
73 | 11 | 2026-09-28 | Evidence + senior narrative | Evidence hardening | Run adversarial, safety, data-quality or baseline comparison. | Write failure analysis and decide public claim limits. | Fix or document limitation | Evaluation report entry | G5 | Not Started | 0
74 | 11 | 2026-09-29 | Evidence + senior narrative | Historical portfolio | Convert one real product into a safe, quantified case study. | Verify personal role, reusable logic, adoption and confidentiality. | Update portfolio site content | Credible historical proof | G5 | Not Started | 0
75 | 11 | 2026-09-30 | Evidence + senior narrative | Senior narrative | Practice the 15-minute Google thesis and three probing questions. | Record, critique and rewrite weak sections. | Update talk track and evidence links | Interview-ready answer | G5 | Not Started | 0
76 | 11 | 2026-10-01 | Evidence + senior narrative | Evidence hardening | Run adversarial, safety, data-quality or baseline comparison. | Write failure analysis and decide public claim limits. | Fix or document limitation | Evaluation report entry | G5 | Not Started | 0
77 | 11 | 2026-10-02 | Evidence + senior narrative | Historical portfolio | Convert one real product into a safe, quantified case study. | Verify personal role, reusable logic, adoption and confidentiality. | Update portfolio site content | Credible historical proof | G5 | Not Started | 0
78 | 12 | 2026-10-03 | Evidence + senior narrative | Senior narrative | Practice the 15-minute Google thesis and three probing questions. | Record, critique and rewrite weak sections. | Update talk track and evidence links | Interview-ready answer | G5 | Not Started | 0
79 | 12 | 2026-10-04 | Sponsorship + launch | Internal sponsorship | Prepare precise named-team introduction request. | Meet insider/reviewer or refine sponsorship package. | Update referral brief and role mapping | Sponsor signal or gap list | G6 | Not Started | 0
80 | 12 | 2026-10-05 | Sponsorship + launch | Public launch | Finish one high-quality public asset. | Evidence, originality, IP and executive-language review. | Polish repository/paper/demo | Publish-ready asset | G7 | Not Started | 0
81 | 12 | 2026-10-06 | Sponsorship + launch | Mock interview | Run role-specific executive/product/technical mock. | Convert every weak answer into a documented remediation. | Update interview bank | Scored mock and improved answer | G6 | Not Started | 0
82 | 12 | 2026-10-07 | Sponsorship + launch | Internal sponsorship | Prepare precise named-team introduction request. | Meet insider/reviewer or refine sponsorship package. | Update referral brief and role mapping | Sponsor signal or gap list | G6 | Not Started | 0
83 | 12 | 2026-10-08 | Sponsorship + launch | Public launch | Finish one high-quality public asset. | Evidence, originality, IP and executive-language review. | Polish repository/paper/demo | Publish-ready asset | G7 | Not Started | 0
84 | 12 | 2026-10-09 | Sponsorship + launch | Mock interview | Run role-specific executive/product/technical mock. | Convert every weak answer into a documented remediation. | Update interview bank | Scored mock and improved answer | G6 | Not Started | 0
85 | 13 | 2026-10-10 | Sponsorship + launch | Internal sponsorship | Prepare precise named-team introduction request. | Meet insider/reviewer or refine sponsorship package. | Update referral brief and role mapping | Sponsor signal or gap list | G6 | Not Started | 0
86 | 13 | 2026-10-11 | Sponsorship + launch | Public launch | Finish one high-quality public asset. | Evidence, originality, IP and executive-language review. | Polish repository/paper/demo | Publish-ready asset | G7 | Not Started | 0
87 | 13 | 2026-10-12 | Sponsorship + launch | Mock interview | Run role-specific executive/product/technical mock. | Convert every weak answer into a documented remediation. | Update interview bank | Scored mock and improved answer | G6 | Not Started | 0
88 | 13 | 2026-10-13 | Sponsorship + launch | Internal sponsorship | Prepare precise named-team introduction request. | Meet insider/reviewer or refine sponsorship package. | Update referral brief and role mapping | Sponsor signal or gap list | G6 | Not Started | 0
89 | 13 | 2026-10-14 | Sponsorship + launch | Public launch | Finish one high-quality public asset. | Evidence, originality, IP and executive-language review. | Polish repository/paper/demo | Publish-ready asset | G7 | Not Started | 0
90 | 13 | 2026-10-15 | Sponsorship + launch | Mock interview | Run role-specific executive/product/technical mock. | Convert every weak answer into a documented remediation. | Update interview bank | Scored mock and improved answer | G6 | Not Started | 0

## Product Portfolio
Product | 90-day state | Founder effort % | Buyer | Core decision | Google foundation | Non-Google differentiation | Validation minimum | Product proof | Technical proof | Economic proof | Public artifact | Kill / narrow condition | Status | Score /100
Decision360 CPG | Public beta | 45 | CSCO / VP Demand Planning | Which demand/inventory intervention should we take, with what confidence and value? | BigQuery, Gemini Enterprise Agent Platform, ADK, Agent Runtime, Cloud Run | Decision value, probabilistic scenarios, approval/outcome learning and interoperability with existing planning engines | 6 practitioners; 3 repeat reviewers; 3 unguided tests | Five workflows and six-week pilot | Secure deployment, evaluation, traceability and cost | Service, working capital, planner time and Google consumption | Repo + demo + case study + executive brief | If users cannot independently complete five workflows, cut scope until they can. | Not Started | 0
Agent Benchmark | Public alpha | 25 | Chief AI Officer / agent product owner | Is this agent improving decisions and business outcomes, not only task success? | ADK evaluation, trajectories, Agent Platform evaluation | Regret, calibration, realized value, override quality, actionability, governance and no opaque total score | 3 agent/platform experts; one academic/decision-science reviewer | 40 tasks and reproducible multidimensional scorecards | Runner, reference agents, metric unit tests | Trust, risk reduction and faster enterprise deployment | Repo + position paper + benchmark results | If novelty duplicates Google evaluation, narrow to decision/economic metrics only. | Not Started | 0
Transformation Mapper | Demonstrable prototype | 18 | CIO / Transformation Officer | Which AI opportunities should we pursue, sequence, buy/build/partner or reject? | Gemini Enterprise, connectors, custom agents, BigQuery | Evidence trace, transparent scoring, no-build option and transformation accountability | 3 transformation leaders; 2 repeat reviews | Evidence→opportunity→score→roadmap flow | Citation accuracy, baseline comparison and sensitivity | Time-to-priority, avoided waste and Google pursuit acceleration | Repo + demo + case study | If output resembles generic LLM brainstorming, stop and rebuild evidence model. | Not Started | 0
Commerce Growth | Vertical demonstration | 12 | Chief Growth Officer / Category VP | Which catalog, assortment or product gaps block demand and agent discovery? | AI Commerce Search, catalog/events, Gemini, BigQuery | Manufacturer/category strategy and athlete-nutrition product opportunity—not personalized medical advice | 2 commerce/CPG leaders; 1 nutrition expert | Intent→gap→opportunity→simulation vertical demo | Synthetic catalog/events and transparent scoring | Discoverability, conversion and assortment opportunity | Repo/spec + vertical demo + market brief | If buyer/use case remains broad, keep as research specification only. | Not Started | 0

## Design Partner Program
ID | Product | Reviewer profile | Target count | Round | Hypothesis to test | Evidence required | Exact ask | Scheduled date | Interview date | Status | Product change / result
DP-01 | Decision360 CPG | Demand Planning / Supply Chain leader | 3 | Pre-build | Problem, buyer, current workflow and five highest-value decisions | Current process, pain, metrics, objections and willingness for second review | 45-minute structured discovery + permission for follow-up |  |  | Not Started
DP-02 | Decision360 CPG | Finance / Working Capital leader | 1 | Pre-build | Economic value and trade-offs are credible | Cost/service trade-offs, current ownership and value measurement | 30-minute value interview |  |  | Not Started
DP-03 | Decision360 CPG | Data / Architecture leader | 1 | Pre-build | Integration and governance assumptions are realistic | System landscape, data constraints, Azure coexistence and security | 30-minute architecture challenge |  |  | Not Started
DP-04 | Decision360 CPG | Repeat reviewers | 3 | Post-MVP | Product can be used without founder narration | Observed task completion, confusion, rejection and desired next action | Unguided demo test plus 20-minute debrief |  |  | Not Started
DP-05 | Agent Benchmark | Agent platform / governance expert | 3 | Alpha review | Decision metrics are novel, valid and operational | Metric critique, missing failure modes and benchmark gaming risks | 45-minute benchmark review |  |  | Not Started
DP-06 | Agent Benchmark | Decision science / forecasting evaluator | 1 | Alpha review | Regret/calibration/value metrics are correctly defined | Metric validity and ground-truth design | Technical review |  |  | Not Started
DP-07 | Transformation Mapper | CIO / Transformation leader | 3 | Prototype review | Portfolio/scoring workflow is better than existing consulting spreadsheets | Current prioritization, political/adoption realities and no-build cases | 45-minute workflow review |  |  | Not Started
DP-08 | Commerce Growth | CPG/eCommerce/category leader | 2 | Vertical review | Agent-readiness and unmet-need outputs drive real commercial decisions | Catalog gaps, category processes and measurable outcomes | 30-minute vertical review |  |  | Not Started
DP-09 | Commerce Growth | Qualified nutrition/sports expert | 1 | Safety review | Athlete vertical is useful without crossing into unsafe health advice | Boundaries, evidence requirements and user risks | 30-minute expert review |  |  | Not Started
DP-10 | Cross-portfolio | Google/cloud/industry architect | 2 | Final review | Products are technically credible and Google-centered without forced lock-in | Architecture, Google differentiation and hybrid deployment | Portfolio architecture review |  |  | Not Started
DP-11 | Cross-portfolio | Google insider relevant to target role | 2 | Final review | Body of work maps to a real team and senior role | Role/team mapping, level, missing evidence and sponsor comfort | 60-minute launch review |  |  | Not Started
DP-12 | Cross-portfolio | Independent executive reviewer | 1 | Final review | 15-minute thesis is clear, commercially credible and memorable | Narrative, differentiation, credibility and objections | Recorded mock board/CXO pitch |  |  | Not Started

## Competitive Landscape
Product | Competitor / alternative | What it already does well | Why buyer naturally chooses it | Gap we claim | Our defensible difference | Google-specific advantage | Interoperability stance | Evidence needed | Kill criterion | Reviewer verdict | Status | Source URL | Notes
Decision360 CPG | Microsoft Azure / Fabric / Copilot | Enterprise integration, Microsoft estate, commercial familiarity | Already approved, integrated and perceived as economical | No complete probabilistic decision layer across forecast, inventory, approval and outcome | Open decision layer above existing planning engines; decision-value evaluation | BigQuery analytical scale, Gemini agents, Google data/AI strengths | Must coexist with Azure and ERP; no rip-and-replace thesis | Hybrid architecture, cost comparison, buyer interviews | If no Google-specific advantage survives, make product cloud-neutral | Pending | Not Started
Decision360 CPG | SAP IBP / o9 / Kinaxis / Blue Yonder | Established planning workflows and system-of-record integration | Specialist functionality and operational trust | Decision explanation, cross-system evidence, agent workflow and realized decision value | Works above/alongside planning engines; measures interventions and learning | Google can provide open data/agent/application layer | Integrate via APIs and exports; do not replace core planning initially | Workflow comparison and specialist review | If proposition is only a weaker planning suite, stop | Pending | Not Started
Decision360 CPG | Palantir AIP | Ontology, operational workflows, enterprise deployment | Strong application layer and decision operations | CPG-specific probabilistic planning product and transparent open benchmark | Deep domain package and lower implementation burden | Google ecosystem, open components and broader market reach | Acknowledge Palantir strength; compare openness and deployability | Architecture/economic comparison | If Palantir already solves exact workflow better, narrow differentiation | Pending | Not Started
Agent Benchmark | Google Agent Platform evaluation | Task success, final response, trajectory, safety and evaluation flywheel | Native platform integration | Business decision quality, economic utility, calibration, adoption and governance outcomes | Extension layer, not replacement; custom decision metrics and open tasks | Direct integration into Google evaluation workflows | Use Google evals as technical base | Metric mapping to official capabilities | If metrics duplicate native capabilities, remove them | Pending | Not Started
Agent Benchmark | LangSmith / Arize / other observability | Agent traces, evaluation, monitoring and debugging | Mature developer workflows | Decision economics and business outcome standards | Business decision benchmark above observability tools | Google integration plus open provider-neutral contract | Provider-neutral metrics and adapters | Expert review and baseline comparison | If only another observability dashboard, stop | Pending | Not Started
Transformation Mapper | McKinsey/BCG/Accenture/Fractal consulting | Judgment, executive trust, context and implementation support | Accountability and relationships | Repeatable evidence ingestion, transparent scoring and continuous portfolio learning | Productizes discovery while preserving human accountability | Accelerates Google pursuits and partner delivery | Can feed consulting engagements, not replace all advice | CIO interviews and time/value benchmark | If output requires bespoke consultants for every step, narrow claim | Pending | Not Started
Commerce Growth | AI Commerce Search / recommendation platforms | Search relevance, personalization, conversion optimization | Direct commerce KPI impact | Manufacturer category strategy, product opportunity and agent-readiness | Moves upstream into portfolio and innovation decisions | Google commerce data and Gemini reasoning | Works with existing search stack | CPG buyer validation | If no repeatable buyer workflow, keep as research only | Pending | Not Started

## Google Commercial Value
Product | Entry use case | Customer value | Google land motion | Expansion motion | Google services consumed | Why Google vs Azure/AWS | Partner / services pull-through | Target enterprise count | Assumptions to validate | Status | Evidence
Decision360 CPG | Demand/inventory exception decision | Lower service risk, excess inventory and decision time | Land with BigQuery + Gemini decision workflow over selected business unit | Expand to commercial planning, procurement, logistics, finance and additional markets | BigQuery, Gemini/Agent Platform, Cloud Run/Runtime, observability, storage | Open analytics + agent layer; strong data/AI; does not require replacing ERP/planning systems | Google Cloud Consulting, SI integration, industry accelerators | 50 | Data volumes, model calls, workflow frequency, services scope and Azure coexistence | Not Started
Agent Benchmark | Agent governance and release gate | Reduce failed agent deployments and improve trust | Land as evaluation layer in AI platform program | Expand across agent portfolio, online monitoring and governance | Agent Platform evaluation, BigQuery, observability, Runtime | Native extension to Google agent stack with provider-neutral benchmark credibility | AI governance consulting, implementation partners | 100 | Metric usefulness, willingness to pay and native-feature overlap | Not Started
Transformation Mapper | AI portfolio prioritization | Avoid low-value initiatives and speed transformation roadmap | Land through executive discovery and Gemini Enterprise evidence analysis | Expand into delivery governance, data modernization and agent programs | Gemini Enterprise, connectors, BigQuery, agent tools | Strong research/agent/data stack plus repeatable services offer | Consulting pursuit and partner delivery | 40 | Buyer, services model, data access and repeatability | Not Started
Commerce Growth | Catalog/agent-readiness and category opportunity | Higher discoverability, conversion and assortment productivity | Land with AI Commerce Search and catalog diagnostic | Expand to personalization, product innovation, analytics and marketing | AI Commerce Search, BigQuery, Gemini, storage | Google commerce/search heritage and data/AI platform | Retail/CPG partners and implementation | 30 | Access to commerce data, buyer ownership and medical-safety boundary | Not Started
Model input | Decision360 low | Base | High | Unit | Source / validation | Sensitivity | Owner
Annual target enterprises | 10 | 25 | 50 | count | Industry sizing/interviews | High | Rick
Average annual BigQuery + agent consumption per enterprise | 2500000 | 6000000 | 12000000 | ₹ | Architecture and cost model | High | Rick + architect
Professional services / partner pull-through | 5000000 | 15000000 | 30000000 | ₹ | Google/partner validation | High | Rick
Expansion multiplier after initial use case | 1.5 | 2.5 | 4 | x | Land-and-expand hypothesis | High | Rick
Adoption probability | 10% | 25% | 45% | % | Design partner and field validation | Critical | Rick
Scenario | Annual platform consumption | Services pull-through | Combined economic influence | Interpretation
Low | 3750000 | 5000000 | 8750000 | Do not overclaim; use as downside case
Base | 93750000 | 93750000 | 187500000 | Planning case only until field-validated

## Founder Decision Log
Decision ID | Date | Product | Decision | Options considered | Codex / technical recommendation | Business implications | Evidence | Rick decision | Reason | Reversal trigger | Outcome | Status
FD-001 |  | Decision360 CPG | Is Decision360 a planning engine or a decision layer? | Replace planning engine; sit above existing engines; cloud-neutral toolkit | TBD | Replacement expands scope and reduces credibility | Competitive review and buyer interviews | Decision layer above/alongside systems of record | Fits buyer reality, avoids recreating SAP/o9/Kinaxis and supports Azure-heavy clients | Three buyers demand replacement and can justify economics |  | Not Started
FD-002 |  | Agent Benchmark | Should the benchmark produce one overall score? | Single rank; multidimensional scorecard; domain-specific gates | TBD | Single score is marketable but risks hiding critical failures | Risk/governance expert feedback | No default opaque total score | Critical safety/governance failures must remain visible | Reviewers prove a transparent composite improves decisions |  | Not Started
FD-003 |  | Commerce Growth | Should athlete nutrition include individual recommendations? | Personal advice; product/category research only | TBD | Medical risk and evidence burden | Nutrition expert review | Product/category research only | Keeps use case commercially useful and safe | Qualified clinical governance and validated evidence become available |  | Not Started

## Historical Portfolio
Case | Company / context | Problem | User / buyer | Your personal role | Team | Product / solution | Reusable element | Launch / adoption | Business result | Failure / learning | Safe public evidence | IP risk | Status
FX360 | Fractal / forecasting | Fragmented forecasting and decision workflow | Fortune 500 planning leaders | Product conception, domain architecture, executive narrative and build leadership | To document | Sanitized forecasting/decision platform case | Decision workflows, benchmark logic, value translation | To document without confidential detail | Quantify with approved/public figures only | What did not scale or gain adoption? | Sanitized diagram, role, generalized workflow and learning | High | Not Started
Test Ops | AB InBev | Testing operations and process standardization | Technology / operations leaders | To document precisely | To document | Test operations product | Standard operating model and productization | To document | To document | To document | Public-safe case study only | Medium | Not Started
DCCE | Genpact | To reconstruct accurately | To document | To document precisely | To document | DCCE product / capability | Reusable product elements | To document | To document | To document | Public-safe case study only | Medium | Not Started
Remote Job Portal | Independent | Remote job discovery, fit and application friction | India-based global job seekers | Founder/product owner | Codex/AI-assisted build | Automated career intelligence product | Workflow, product benchmark and agent orchestration | Working build status to document | Usage and conversion metrics to establish | Scope, source and trust challenges | Public repo/demo where safe | Low | Not Started
Learning / Tuition Product | Independent | Tutor, student and production/accountability problems | Tutors, parents, students and operators | Founder/product owner | To document | Learning studio/product | Workflow standardization and marketplace/product insight | Build status to document | Metrics to establish | Adoption and focus learning | Public repo/demo where safe | Low | Not Started

## IP Clean-Room Review
Check ID | Product / asset | Question | Required evidence | Risk level | Owner | Legal / employer review needed? | Status | Decision | Public wording | Reviewer
IP-001 | Decision360 | Does any logic, code, UI, dataset, benchmark or terminology reproduce FX360/employer IP? | Independent repo history, synthetic data, clean-room design notes and excluded list | Critical | Rick | Yes | Not Started |  | Independently developed using public concepts and synthetic data; contains no employer/client code or data.
IP-002 | Historical portfolio | Are performance results, client identities and screenshots approved for public use? | Public sources or written approval; otherwise anonymize/generalize | Critical | Rick | Yes | Not Started |  | Results shown only where already public or explicitly approved.
IP-003 | Test Ops / DCCE | Do prior employment agreements restrict public detail or derivative product logic? | Contract/policy review and safe abstraction | High | Rick | Possibly | Not Started |  | Sanitized case study; no proprietary code, data or documents.
IP-004 | All projects | Do repositories imply Google endorsement, partnership or employment? | Naming, logos, README and disclaimer review | High | Rick | No | Not Started |  | Independent open-source research project; not affiliated with or endorsed by Google.
IP-005 | Commerce Growth | Could athlete-nutrition claims be interpreted as medical or dietary treatment advice? | Qualified expert review, disclaimers and evidence taxonomy | Critical | Rick | Possibly | Not Started |  | Product/category research only; not medical or individualized nutrition advice.
IP-006 | All projects | Are licenses compatible with dependencies, datasets and public contribution goals? | Dependency/license scan and chosen project license | High | Codex + Rick | No | Not Started |  | Third-party licenses documented; no restricted data redistributed.

## Codex Execution Backlog
Task ID | Phase | Product | Priority | Workstream | Task | Codex instruction | Inputs | Expected output | Acceptance test | Rick decision required | Evidence artifact | Effort | Due day | Status | Dependency | Failure response
CX-001 | Truth | Launch Package | P0 | Product | Write contribution thesis | Create a one-page thesis describing the enterprise problem layer Google needs, the products that prove it, and the role families that should own it. Avoid job-seeker language. | User background, role research | docs/google_contribution_thesis.md | A Google insider can state the relevant team and role after reading it. | Approve final wording and remove unsupported claims. | One-page thesis | 5 | 5 | Not Started | None | Rewrite after insider feedback.
CX-002 | Truth | Launch Package | P0 | Networking | Create insider calibration pack | Generate questions, one-page profile, target role hypotheses, compensation question and follow-up template. | Contribution thesis | docs/insider_calibration_pack.md | Secures two independent, specific role/level assessments. | Select who to contact and approve message. | Two completed calibrations | 5 | 10 | Not Started | Contribution thesis | Do not progress to role positioning without answers.
CX-003 | Truth | Decision360 CPG | P0 | Customer Validation | Create design-partner discovery kit | Build interview guide, workflow map template, assumption log and evidence scoring. | Decision360 hypothesis | validation/decision360_discovery_kit.md | Six interviews produce comparable evidence and explicit changed assumptions. | Approve buyer profiles and questions. | Interview evidence table | 5 | 7 | Not Started | None | Rewrite PRD if buyer or decision differs.
CX-004 | Truth | Shared Platform | P0 | IP / Legal | Create clean-room protocol | Create excluded sources list, provenance rules, synthetic-data rule, public disclaimer and pre-release checklist. | Employment/product history | docs/clean_room_protocol.md | Every public asset can be traced to independent/public inputs. | Approve exclusions and seek legal review where required. | Signed clean-room checklist | 5 | 12 | Not Started | None | Block public release.
CX-005 | Build | Decision360 CPG | P0 | Product | Create five workflow PRD | Specify five end-to-end buyer workflows, decisions, evidence, failure modes, approval and outcome capture. | Design-partner evidence | products/decision360/PRD.md | Each workflow has user, decision, data, acceptance, business metric and non-goal. | Approve every business rule; Codex must not invent rules. | Approved PRD | 8 | 20 | Not Started | Discovery evidence | Cut any workflow without validated buyer need.
CX-006 | Build | Shared Platform | P0 | Architecture | Build shared evidence and decision contract | Implement schemas for evidence, assumptions, recommendation, approval, outcome, trace, cost and latency. | Approved PRDs | packages/contracts | All four products use versioned schemas and validation tests. | Approve required vs optional fields. | Schema tests and ADR | 8 | 25 | Not Started | Clean-room protocol | Stop product-specific UI until contract works.
CX-007 | Build | Decision360 CPG | P0 | Build | Implement vertical slice 1 | Build synthetic CPG data → risk detection → evidence → recommendation → human approval → outcome ledger using deterministic logic first. | Decision360 PRD, contracts | Working API/UI slice with tests | One scenario runs end to end with no model dependency and complete audit trail. | Approve calculation logic and business meaning. | Demo + automated tests | 13 | 30 | Not Started | Shared contract | Do not add agents until deterministic flow is correct.
CX-008 | Build | Decision360 CPG | P0 | Build | Add Gemini/ADK interaction layer | Add allow-listed tools over validated deterministic services; structured output and refusal rules. | Vertical slice and tool contracts | Agent workflow and trace | Correct tool path ≥90%; no unsupported write action; all recommendations cite evidence. | Approve tool permissions and refusal policy. | Evaluation report | 13 | 38 | Not Started | Vertical slice 1 | Revert to guided workflow if agent reduces reliability.
CX-009 | Build | Decision360 CPG | P0 | Evaluation | Create 60-case decision suite | Normal, disruption, missing data, unsafe, ambiguous, adversarial and Azure-integration cases. | PRD and synthetic data | evals/decision360 + report | Critical safety 100%; workflow completion ≥90%; numeric reconciliation 100%. | Approve public thresholds and claim limits. | Benchmark report | 13 | 45 | Not Started | Agent layer | Block beta if critical thresholds fail.
CX-010 | Build | Decision360 CPG | P0 | Customer Validation | Run three unguided tests | Prepare scripted tasks and capture task completion, confusion, rejection and next-action interest. | Beta build | validation/unguided_results.md | Three relevant users complete five workflows without founder intervention or scope is cut. | Decide release scope based on evidence. | Observed usability evidence | 8 | 48 | Not Started | 60-case suite | Cut features and rerun.
CX-011 | Originality | Agent Benchmark | P0 | Product | Map native Google evaluation vs missing metrics | Create capability map for final response, trajectory, task success, safety, simulation and monitoring versus regret/calibration/value/adoption/governance. | Official Google docs | products/benchmark/native_gap_map.md | No proposed flagship metric duplicates native capability without extension rationale. | Approve unique metric thesis. | Gap map with sources | 5 | 25 | Not Started | None | Delete duplicate metrics.
CX-012 | Originality | Agent Benchmark | P0 | Build | Implement decision metric library | Implement regret, utility, calibration, constraint violations, evidence sufficiency, override quality, actionability and realized value contracts. | Metric definitions | metric package with unit tests | Synthetic cases produce mathematically expected results and critical violations cannot be averaged away. | Approve metric semantics and weights. | Unit tests and examples | 13 | 55 | Not Started | Native gap map | Remove unverifiable metrics.
CX-013 | Originality | Agent Benchmark | P0 | Evaluation | Build 40-task benchmark alpha | Create tasks across supply chain, commerce, finance and transformation with reference baselines and reproducible runner. | Shared contracts and synthetic data | benchmark suite and scorecards | Fresh clone runs sample suite; results reproducible; confidence intervals shown. | Approve task business realism. | Public alpha report | 13 | 62 | Not Started | Metric library | Reduce domains, not metric quality.
CX-014 | Portfolio | Transformation Mapper | P1 | Build | Build evidence-to-opportunity thin slice | Ingest synthetic enterprise evidence, extract cited pains/KPIs, propose opportunities, transparently score and produce no-build option. | Synthetic evidence pack | Prototype and comparison baseline | Every opportunity has citations; unsupported rate <10%; static generic-LLM baseline compared. | Approve scoring factors and no-build rules. | Prototype demo and report | 13 | 63 | Not Started | Shared contracts | Stop if output remains generic.
CX-015 | Portfolio | Commerce Growth | P1 | Product | Build athlete nutrition market vertical | Create product/category research workflow: need-state taxonomy, catalog readiness, gaps and product opportunity with strict medical boundary. | Synthetic catalog, expert safety input | Vertical demo/spec | No individualized health advice; every opportunity ties to market/catalog evidence. | Approve buyer, boundary and claims. | Demo + safety review | 8 | 65 | Not Started | Clean-room protocol | Keep as specification if validation is weak.
CX-016 | Evidence | Google Commercial Story | P0 | Competition | Build Google-vs-alternatives defence | Create product-by-product comparison with Azure, specialist platforms, Palantir, Databricks/Snowflake and consulting alternatives; include hybrid architecture. | Competitive matrix and reviews | docs/google_centered_but_interoperable.md | Can answer why Google, why not Google, and how Azure-heavy clients coexist. | Approve honest disadvantages. | Competitive defence | 8 | 68 | Not Started | External review | Make product cloud-neutral if Google advantage is forced.
CX-017 | Evidence | Google Commercial Story | P0 | Product | Build Google economic model | Estimate land motion, consumption, services pull-through, expansion and sensitivity with transparent assumptions. | Architecture and buyer inputs | commercial/google_value_model.md + spreadsheet inputs | All assumptions labeled; low/base/high; no invented customer savings. | Approve assumptions and public wording. | Economic model | 8 | 70 | Not Started | Competitive defence | Use qualitative case if inputs are not validated.
CX-018 | Evidence | Historical Portfolio | P0 | Product | Create five sanitized case studies | Document FX360, Test Ops, DCCE, remote jobs and learning product with problem, role, team, launch, result, learning and reusable pattern. | Personal records and approved facts | portfolio/case_studies/*.md | Personal contribution is specific; unsupported results removed; IP review passes. | Approve every fact and boundary. | Portfolio site content | 13 | 72 | Not Started | Clean-room protocol | Anonymize or omit risky details.
CX-019 | Evidence | Launch Package | P0 | Public Launch | Create 15-minute thesis presentation | Build narrative: real-world problem gap, four solutions, evidence, Google economics, historical pattern, role contribution and ask. | All evidence | launch/google_thesis_talk.md | Delivered in 15 minutes; survives 10 executive/product/technical probes. | Approve final thesis and ask. | Recorded mock and score | 8 | 76 | Not Started | Historical portfolio | Rewrite based on mocks.
CX-020 | Launch | Launch Package | P0 | Networking | Create named-team sponsor package | One-page role match, portfolio links, why Google, likely level, compensation calibration and exact introduction ask. | Thesis, role calibration, public assets | launch/sponsor_brief.md | Relevant insider states willingness to introduce or gives explicit remaining gaps. | Choose only named team/role; no generic referral. | Sponsor response | 5 | 82 | Not Started | Thesis presentation | Delay application if sponsor not comfortable.
CX-021 | Launch | Decision360 CPG | P0 | Public Launch | Launch flagship beta | Complete README, demo, architecture, pilot, evaluation, security, IP disclaimer, contribution guide and roadmap. | Validated beta | Public-ready repo package | All gates pass; no confidential material; five workflows and evidence are visible. | Final release approval. | Public beta | 13 | 88 | Not Started | Unguided tests, IP review | Selective/private beta if any gate fails.
CX-022 | Launch | Agent Benchmark | P0 | Public Launch | Launch benchmark alpha and paper | Publish metric taxonomy, native gap map, runner, tasks, findings, limitations and contribution process. | Benchmark alpha | Public-ready repo + paper | Reproducible sample run; novelty clearly stated; no universal-score overclaim. | Final paper approval. | Public alpha | 13 | 88 | Not Started | 40-task suite | Publish paper first if code quality lags.
CX-023 | Launch | Launch Package | P0 | Public Launch | Publish portfolio and launch sequence | Launch portfolio site, four project pages, five-post sequence, demos and executive briefs. | All launch assets | Public portfolio | Coherent identity; each claim links to evidence; CTA targets practitioners and Google/industry leaders. | Approve timing and messages. | Live portfolio and posts | 8 | 90 | Not Started | Flagship and benchmark | Delay broad promotion if evidence is weak.

## Launch & Prominence
Asset | Primary audience | Claim | Evidence required | Format | Due day | Quality gate | Status | Publish date | URL | Distribution | Success signal
GroundAI portfolio site | Google leaders, industry executives, collaborators | This is a long-running pattern of productizing real enterprise problems. | Five historical cases plus four new products | Website/GitHub Pages | 86 | Every claim sourced or clearly marked as thesis | Not Started |  |  | LinkedIn, direct outreach, Google contacts | Relevant introductions and practitioner engagement
Decision360 beta | Supply-chain executives and Google industry teams | A governed decision layer can improve planning decisions without replacing systems of record. | Five workflows, validation, evaluation and pilot economics | Public repo + demo | 88 | Unguided tests and IP gate pass | Not Started |  |  | Targeted practitioner launch | Design partner requests or serious reviews
Decision Agent Benchmark alpha | AI platform and governance community | Enterprise agents must be evaluated on decision and economic outcomes beyond task success. | Native capability map, 40 tasks, reproducible metrics | Repo + paper | 88 | Novelty and mathematical validity reviewed | Not Started |  |  | AI/agent communities and direct experts | Contributors, citations, expert critique
Transformation Mapper prototype | CIO and transformation community | AI opportunity selection can be evidence-backed and productized without pretending to replace judgment. | Baseline comparison and cited opportunity workflow | Repo + demo | 89 | Unsupported-rate threshold passes | Not Started |  |  | Transformation leaders | Pilot conversations
Commerce Growth vertical | CPG/eCommerce/innovation leaders | Commerce infrastructure can be extended into agent-readiness and category opportunity. | Expert safety review and market/catalog evidence | Demo + brief | 89 | No medical or unsupported health claims | Not Started |  |  | CPG and sports-nutrition network | Expert feedback and buyer interest
15-minute Google thesis | Google insiders and hiring leaders | I can help Google turn horizontal AI into implementable industry products and repeatable transformations. | All portfolio evidence and commercial model | Recorded talk + one-pager | 80 | Mock score ≥4/5 across executive, product and technical reviewers | Not Started |  |  | Direct sponsor outreach | Named team introduction
LinkedIn five-part series | Market and professional network | Horizontal AI needs a measurable application and decision layer. | Flagship and benchmark evidence | Five posts | 90 | No generic hype; each post contains an artifact or result | Not Started |  |  | Scheduled sequence | Meaningful comments from practitioners

## Google Launch Package
Package item | Target role / team | Purpose | Required content | Evidence link | Reviewer | Mock score /5 | Status | Due day | Failure threshold | Recovery
Google-specific CV | Pursuit/Transformation/Industry/Consulting | Pass screening at senior scope | Historical product pattern, CXO work, repeatable assets, implementation leadership, quantified outcomes |  | Google insider | 0 | Not Started | 75 | <4/5 | Rewrite achievements and role hypothesis
One-page sponsor brief | Named team/role | Make an introduction easy and defensible | Why this team; contribution; evidence; level; exact ask |  | Google insider | 0 | Not Started | 82 | Sponsor unwilling | Address explicit gap before referral
15-minute thesis talk | Hiring leader / sponsor | Demonstrate thought leadership and executive clarity | Problem gap, products, evidence, Google economics, historical pattern, ask |  | Executive reviewer | 0 | Not Started | 76 | <4/5 | Re-record after three mocks
Product deep dive | Industry/product team | Prove product judgment and implementation leadership | Decision360 PRD, decisions, failures, validation, architecture and economics |  | Product leader | 0 | Not Started | 80 | <4/5 | Strengthen founder decision log
Technical defence | Architect / CE / FDE reviewer | Show you cannot be bluffed and can lead engineers | Data flow, IAM, tools, agent vs deterministic, evaluation, scale, cost, hybrid integration |  | Cloud architect | 0 | Not Started | 80 | <3.5/5 | Daily technical drills
Commercial pursuit case | Pursuit / Consulting | Prove opportunity shaping and services commercialization | Discovery, value case, proposal, adoption roadmap, Google consumption and partner orchestration |  | Sales/consulting leader | 0 | Not Started | 82 | <4/5 | Rebuild commercial model
12 leadership stories | All senior roles | Pass behavioural and leadership probing | Ambiguity, failure, executive dissent, product launch, adoption, people, ethics, scale and learning |  | Mock interviewer | 0 | Not Started | 84 | Any story collapses | Rewrite with personal decisions and evidence
Compensation/level decision sheet | Recruiter / self | Avoid under-level entry | Current scope, target level, package components, walk-away conditions and alternatives |  | Trusted advisor | 0 | Not Started | 85 | No reliable calibration | Do not apply yet

## Lists
Status | Priority | Product | Workstream | Evidence | Gate | Reviewer Type | Risk | Owner | Outcome
Not Started | P0 | Decision360 CPG | Product | None | Pending | Google Insider | Low | Rick | No
In Progress | P1 | Agent Benchmark | Architecture | Partial | Pass | Industry Expert | Medium | Codex | Partial
Completed | P2 | Transformation Mapper | Build | Strong | Fail | Design Partner | High | Rick + Codex | Yes
Blocked |  | Commerce Growth | Evaluation |  |  | Mock Interviewer | Critical
Deferred |  | Shared Platform | Customer Validation
|  | Historical Portfolio | Competition
|  | Google Commercial Story | IP / Legal
|  | Launch Package | Public Launch
Networking