## Dashboard
ContexureEarth Tutor Project Command Center
Purpose | Vision-linked project planner covering what is already done, what remains, dependencies, launch gates, risks, research, and metrics.
North Star | Weekly completed tutor actions
Last Updated | 2026-06-13
KPI | Value | Meaning
Total Tasks | 96 | All tracked tasks
Done Tasks | 22 | Completed BizzNexx/ContexureEarth work
Open P0 Tasks | 44 | Critical work left
Blocked Tasks | 0 | Needs founder/engineering attention
Open Critical Risks | 0 | No launch with critical open risk
Private Beta Gate Date | 2026-09-06 | Current target gate
Phase | Start | End | Mission
Already Done / Existing BizzNexx Assets | 2026-06-01 | 2026-06-13
Foundation & Product Definition | 2026-06-15 | 2026-06-28
Concierge Prototype | 2026-06-29 | 2026-07-19
Private Beta | 2026-07-20 | 2026-09-06
Paid Pilot | 2026-09-07 | 2026-12-13
Public Launch V1 | 2026-12-14 | 2027-03-14
Growth & Intelligence V1 | 2027-03-15 | 2027-09-12
Learning Context V1 | 2027-09-13 | 2028-03-12
Institution Expansion | 2028-03-13 | 2029-06-30

## Master Plan
Task ID | Phase | Workstream | Title | Description | Owner | Priority | Status | Start | End | Dependencies | Effort | Acceptance Criteria | Validation Signal | Vision Link | Notes
DONE-001 | D0 | Strategy & Product Definition | Learning Studio strategy created | Created Learning Studio business ontology, strategy plan, execution plan, and beta rollout readiness plan. | Founder/Product | P0 | Done | 2026-06-01 | 2026-06-06 |  | 3 | Strategy docs exist and define tutor wedge. | Learning Studio is defined as trust, trial, parent communication, and recurring-fee business. | V1/V2/V4/V5
DONE-002 | D0 | Strategy & Product Definition | First validation wedge narrowed | Narrowed initial beta wedge to Ananya Learning Studio and tutor/coach persona. | Founder/Product | P0 | Done | 2026-06-05 | 2026-06-06 | DONE-001 | 3 | Ananya is the demo anchor. | Product can be reviewed through one concrete tutor story. | V1
DONE-003 | D0 | Frontend Engineering | Parallel Beta Studio UI added | Added Beta Studio tab for tutor businesses while preserving existing prototype screens. | Frontend | P0 | Done | 2026-06-06 | 2026-06-07 | DONE-002 | 3 | Tutor-specific surface exists. | Reviewer can open Ananya Learning Studio Beta Studio. | V1/V7
DONE-004 | D0 | Frontend Engineering | Parent-ready Learning Studio surface built | Added teacher credibility, proof, course cards, trial inquiry form, parent journey, trial action queue, monthly fee actions, and FAQ. | Frontend/Product | P0 | Done | 2026-06-06 | 2026-06-07 | DONE-003 | 3 | Core tutor beta UI exists. | The demo can show parent page to fee workflow. | V1/V2/V4/V5/V6
DONE-005 | D0 | Auth, Privacy & Trust | Beta safety notes added | Added beta disclaimer, beta terms view, and inquiry consent/data-use copy. | Security/Product | P0 | Done | 2026-06-07 | 2026-06-08 | DONE-004 | 3 | Beta users see scope and data-use notes. | No real-data review without safety copy. | V7
DONE-006 | D0 | Backend & Data Model | Ananya seed data enriched | Aligned backend demo seed data with richer Learning Studio story, persona statuses, and message templates. | Backend/Product | P0 | Done | 2026-06-07 | 2026-06-08 | DONE-004 | 3 | Seed data supports realistic demo. | Ananya data includes courses, proof, FAQs, leads, payments. | V1/V2/V5
DONE-007 | D0 | Auth, Privacy & Trust | Private beta access controls added | Added optional frontend access code, backend API key gate, environment examples, and production-safe settings hooks. | Security/Backend/Frontend | P0 | Done | 2026-06-08 | 2026-06-09 | DONE-005 | 3 | Beta access can be restricted. | Demo can be shared with selected reviewers only. | V7
DONE-008 | D0 | Infrastructure & Deployment | Deployment blueprint prepared | Added Postgres support, Gunicorn, static root, render.yaml, health endpoint, and deployment docs. | Engineering | P0 | Done | 2026-06-09 | 2026-06-10 | DONE-007 | 3 | Render deployment path exists. | Backend health endpoint available. | V7
DONE-009 | D0 | Infrastructure & Deployment | GitHub Actions CI added | Added frontend build and backend checks on main. | Engineering/QA | P0 | Done | 2026-06-10 | 2026-06-10 | DONE-008 | 3 | CI workflow exists. | Build/check pipeline can run on main. | V7
DONE-010 | D0 | Infrastructure & Deployment | GitHub Pages preview workflow added | Added no-new-cloud-account frontend preview path for UI-only guided review. | Engineering | P1 | Done | 2026-06-10 | 2026-06-10 | DONE-009 | 3 | Preview workflow and guide exist. | UI can be reviewed without backend hosting. | V1
DONE-011 | D0 | Documentation & Handoff | Root README updated | Updated README with BizzNexx product shape, Learning Studio beta, run commands, and deployment paths. | Documentation | P0 | Done | 2026-06-10 | 2026-06-11 | DONE-008 | 3 | README gives clear project entry. | New reviewer can understand current status. | V7
DONE-012 | D0 | Operator Setup & Support | Beta review guide created | Created guided review script for tutor beta reviews. | Operations/Product | P0 | Done | 2026-06-11 | 2026-06-11 | DONE-004 | 3 | Review guide covers parent page, inquiry, action queue, fees, and WTP. | Beta calls have a consistent script. | V1/V2/V5
DONE-013 | D0 | Operator Setup & Support | Beta feedback form created | Created structured beta feedback form with workflow fit, commercial signal, trust/safety, and product gaps. | Operations/Product | P0 | Done | 2026-06-11 | 2026-06-11 | DONE-012 | 3 | Feedback form can be used per reviewer. | WTP and product-fit signals are captured. | V7
DONE-014 | D0 | QA, Testing & Release Gates | Private beta QA checklist created | Created hosted deployment QA checks before sharing beta URL. | QA | P0 | Done | 2026-06-11 | 2026-06-12 | DONE-008 | 3 | Checklist covers HTTPS, access gate, Ananya, inquiry, message, payment, beta terms. | No beta sharing without QA pass. | V7
DONE-015 | D0 | Strategy & Product Definition | Tutor growth feature universe created | Created feature strategy, persona mapping, heatmap, ranking model, and top build order. | Product | P0 | Done | 2026-06-12 | 2026-06-12 | DONE-001 | 3 | Feature universe and ranking are documented. | MVP spine is clear. | V1-V8
DONE-016 | D0 | Strategy & Product Definition | Production accountable tasklist created | Created accountable workstreams across product, UX, FE, BE, auth, analytics, QA, infra, ops, support, GTM, and risk. | Product | P0 | Done | 2026-06-12 | 2026-06-13 | DONE-015 | 3 | Production task board exists. | Team can execute using task IDs. | V7
DONE-017 | D0 | Documentation & Handoff | Team handoff guide created | Created TEAM_HANDOFF_START_HERE.md with mission, decisions, MVP spine, first tasks, repo structure, and QA gates. | Documentation/Product | P0 | Done | 2026-06-13 | 2026-06-13 | DONE-016 | 3 | Team entry point exists. | New contributor can start from handoff guide. | V7
DONE-018 | D0 | Strategy & Product Definition | ContexureEarth vision mind map created | Created product vision mind map and renamed vision file under ContexureEarth. | Founder/Product | P1 | Done | 2026-06-13 | 2026-06-13 |  | 3 | Vision file exists under final name. | Long-term learning intelligence direction captured. | V8/V9/V10
DONE-019 | D0 | Strategy & Product Definition | ContexureEarth tutor roadmap created | Created research-backed tutor product roadmap linking BizzNexx work to ContexureEarth. | Product | P1 | Done | 2026-06-13 | 2026-06-13 | DONE-018 | 3 | Roadmap covers research, build, GTM, launch, post-launch. | Execution path is visible. | V1-V10
DONE-020 | D0 | Strategy & Product Definition | BizzNexx critical evaluation created | Evaluated what BizzNexx already achieves and how it should evolve into ContexureEarth Tutor. | Product | P1 | Done | 2026-06-13 | 2026-06-13 | DONE-019 | 3 | Evaluation gives brand architecture and product migration recommendation. | Decision: ContexureEarth public brand; BizzNexx operating engine. | V1-V10
DONE-021 | D0 | QA, Testing & Release Gates | Initial verification passed | npm run build, Django check, collectstatic dry run, compileall, and local UI response were verified previously. | Engineering/QA | P0 | Done | 2026-06-10 | 2026-06-13 | DONE-009 | 3 | Verification evidence recorded in project log. | Prototype is stable enough for deployment prep. | V7
DONE-022 | D0 | Marketing, Sales & Launch | Code pushed to GitHub | Project log records code pushed with key commits for strategy, UI, safety, deployment, and preview. | Engineering | P0 | Done | 2026-06-10 | 2026-06-13 | DONE-021 | 3 | Commits are recorded. | Remote repo has current work. | V7
IMD-001 | P0 | Infrastructure & Deployment | Create Render Blueprint deployment | Create Render Blueprint from GitHub and let it provision frontend, backend, and Postgres database. | Engineering | P0 | Not Started | 2026-06-15 | 2026-06-17 | DONE-008,DONE-022 | 4 | Render services exist and deploy successfully. | Hosted API and frontend URLs available. | V7
IMD-002 | P0 | Auth, Privacy & Trust | Wire beta API keys | Copy backend BIZZNEXX_BETA_API_KEY to frontend VITE_BETA_API_KEY and set VITE_BETA_ACCESS_CODE. | Security/Engineering | P0 | Not Started | 2026-06-17 | 2026-06-18 | IMD-001,DONE-007 | 2 | Frontend and backend keys match; access gate works. | Unauthorized beta access blocked. | V7
IMD-003 | P0 | QA, Testing & Release Gates | Run hosted beta QA checklist | Confirm HTTPS, access gate, Ananya, Beta Studio, inquiry submit, lead creation, message preview, mark paid, beta terms. | QA/Product | P0 | Not Started | 2026-06-18 | 2026-06-20 | IMD-002,DONE-014 | 3 | QA checklist completed with pass/fail evidence. | No beta user sees broken hosted flow. | V7
IMD-004 | P0 | Research & Customer Discovery | Recruit first 5 tutor reviewers | Use existing networks to schedule guided review calls with academic tutors/coaches. | Founder/Research | P0 | Not Started | 2026-06-18 | 2026-06-24 | DONE-012,DONE-013 | 3 | 5 calls scheduled or completed. | At least 3 reviewers fit target ICP. | V1/V2/V5
IMD-005 | P0 | Research & Customer Discovery | Capture beta feedback in structured form | Use BETA_FEEDBACK_FORM for every reviewer and summarize share-worthiness, WTP, trust, and gaps. | Research/Product | P0 | Not Started | 2026-06-20 | 2026-06-28 | IMD-003,IMD-004 | 3 | Each review has completed feedback form. | Evidence informs next sprint. | V7
IMD-006 | P0 | Strategy & Product Definition | Founder decision: brand architecture | Confirm whether public brand is ContexureEarth Tutor with BizzNexx as internal/legacy engine. | Founder | P0 | Not Started | 2026-06-20 | 2026-06-22 | DONE-020 | 2 | Decision recorded in roadmap and handoff docs. | No confusion in UI/demo language. | V1-V10
IMD-007 | P0 | UX, Design & Copy | UI copy pass for ContexureEarth Tutor | Replace generic microbusiness language in tutor path with learner, parent, course, batch, fee cycle, operating rhythm. | UX/Product | P0 | Not Started | 2026-06-22 | 2026-06-27 | IMD-006,FE-001 | 4 | Tutor demo uses education-native language. | Reviewers do not perceive it as generic CRM. | V1/V8
C-001 | P0 | Frontend Engineering | Audit current frontend architecture | Identify routes, state, API usage, design debt, responsive gaps, and what can be reused. | Frontend | P0 | Not Started | 2026-06-15 | 2026-06-18 | DONE-004 | 4 | Frontend audit is documented. | Large implementation changes have a clear base. | V7
D-001 | P0 | Backend & Data Model | Audit backend models/APIs | Identify model gaps, workflow gaps, auth gaps, migration risks, and generic-to-education naming pressure. | Backend | P0 | Not Started | 2026-06-15 | 2026-06-18 | DONE-006 | 4 | Backend audit is documented. | Tenant/auth/model decisions can be made. | V7/V8
A-001 | P0 | Strategy & Product Definition | Define production personas | Document academic tutor, exam coach, hobby teacher, skill trainer, fitness trainer, corporate trainer, and priority order. | Product | P0 | Not Started | 2026-06-15 | 2026-06-17 | DONE-015 | 2 | Persona definitions are approved. | P-AST remains first ICP unless evidence changes. | V1
A-004 | P0 | Strategy & Product Definition | Map public visitor journey | Map parent path from shared link to inquiry, trial CTA, confirmation, and WhatsApp handoff. | Product/UX | P0 | Not Started | 2026-06-17 | 2026-06-20 | A-001 | 3 | Journey includes trust, course fit, fee clarity, trial, and privacy. | Parent can understand next step in 30 seconds. | V1/V2
A-005 | P0 | Strategy & Product Definition | Map owner inquiry-to-fee journey | Map owner path from inquiry to trial to enrollment to fee tracking and proof/referral prompt. | Product/UX | P0 | Not Started | 2026-06-17 | 2026-06-21 | A-001 | 3 | Every owner step has status, next action, and message template. | Owner knows what to do today. | V2/V4/V5/V6/V7
D-002 | P0 | Backend & Data Model | Define tenant/account model | Decide account, owner, operator, support, tutor studio boundaries and data isolation rules. | Backend/Security | P0 | Not Started | 2026-06-19 | 2026-06-24 | D-001 | 5 | Multi-tutor data isolation is designed. | No real beta without tenant boundary. | V7
E-001 | P0 | Auth, Privacy & Trust | Choose production auth approach | Choose email/password, OTP, managed auth, or phased approach for owner/operator dashboard. | Security/Backend | P0 | Not Started | 2026-06-22 | 2026-06-26 | D-002 | 4 | Auth decision covers roles, recovery, beta path, and production migration. | Owner dashboard protected. | V7
N-001 | P0 | Infrastructure & Deployment | Choose production hosting architecture | Decide staging/production deployment, database, static assets, backups, monitoring, domain, rollback. | Engineering | P0 | Not Started | 2026-06-22 | 2026-06-27 | D-001,E-001 | 4 | Hosting architecture is approved. | Staging can be created confidently. | V7
B-001 | P0 | UX, Design & Copy | Define ContexureEarth Tutor visual direction | Set calm, credible, parent-friendly, mobile-first, education-native design principles. | UX | P0 | Not Started | 2026-06-19 | 2026-06-23 | IMD-006 | 3 | Moodboard/design principles approved. | Tutor would not be embarrassed to share page. | V1
B-002 | P0 | UX, Design & Copy | Responsive layout system | Define layout system for public page, owner dashboard, and operator console across mobile/desktop widths. | UX/Frontend | P0 | Not Started | 2026-06-24 | 2026-07-01 | B-001,C-001 | 5 | Layouts work at 360, 390, 768, 1024, 1440 widths. | No text overlap or awkward wrapping. | V1/V7
D-004 | P0 | Backend & Data Model | Define Course/Batch model | Define course, batch, schedule, capacity, fee policy, board/class/subject fields. | Backend/Product | P0 | Not Started | 2026-06-25 | 2026-07-02 | D-002,A-005 | 5 | Model supports academic tutor MVP and future exam/hobby variants. | Course cards can be API-backed. | V1/V2
D-005 | P0 | Backend & Data Model | Define Inquiry model | Define structured parent inquiry with academic context, consent, source, duplicate detection path. | Backend/Product | P0 | Not Started | 2026-06-25 | 2026-07-02 | D-002,A-004 | 5 | Inquiry stores class, board, subject, concern, timing, trial interest, source. | Owner avoids repeated basic questions. | V2
D-006 | P0 | Backend & Data Model | Define Lead/Trial states | Define parent inquiry, contacted, trial proposed, scheduled, attended, no-show, enrolled, lost, follow-later states. | Backend/Product | P0 | Not Started | 2026-06-28 | 2026-07-05 | D-005,A-005 | 5 | States cover inquiry-to-enrollment journey. | Trial outcomes are measurable. | V4
F-003 | P0 | WhatsApp & Messaging | Create WhatsApp template library | Create first response, trial options, trial reminder, post-trial, fee reminder, progress, proof, referral messages. | Product/Copy | P0 | Not Started | 2026-06-28 | 2026-07-04 | A-005,IMD-005 | 4 | Templates are polite, editable, parent-safe, context-aware. | Tutors say tone feels natural. | V3/V4/V5/V6
C-003 | P0 | Frontend Engineering | Implement public studio page route | Productionize share-ready public page from API-backed tutor profile, courses, proof, FAQ, and CTA. | Frontend | P0 | Not Started | 2026-07-01 | 2026-07-12 | B-002,D-004 | 7 | Page renders loading, error, fallback, and published states. | Tutor says they would share page. | V1
C-004 | P0 | Frontend Engineering | Implement tutor inquiry flow | Create mobile-friendly inquiry form and confirmation state with consent and source tracking. | Frontend | P0 | Not Started | 2026-07-08 | 2026-07-18 | C-003,D-005 | 6 | Inquiry submits successfully and creates backend lead. | Parent knows what happens next. | V2
F-001 | P0 | WhatsApp & Messaging | Implement manual WhatsApp click-to-chat | Open WhatsApp with prefilled context from inquiry/trial/fee action and copy fallback. | Frontend | P0 | Not Started | 2026-07-12 | 2026-07-20 | C-004,F-003 | 5 | Owner can open/edit/copy WhatsApp messages. | Manual handoff works before API automation. | V3
C-005 | P0 | Frontend Engineering | Implement owner Today dashboard | Create action queue for new inquiries, trials, fee dues, overdue payments, proof/referral prompts. | Frontend | P0 | Not Started | 2026-07-14 | 2026-07-25 | A-005,D-006,F-001 | 7 | Owner sees actionable cards and can update statuses. | Owner knows what needs attention in under 30 seconds. | V7
C-006 | P0 | Frontend Engineering | Implement leads and trial workflow UI | Owner can move inquiry through contacted, trial, enrolled, lost, follow-later states. | Frontend | P0 | Not Started | 2026-07-22 | 2026-08-02 | C-005,D-006 | 6 | Owner can update trial statuses without confusion. | Trial queue has no stale invisible leads. | V4
C-007 | P0 | Frontend Engineering | Implement student/learner memory UI | Show lightweight learner profile and notes connected to inquiry, enrollment, parent contact, next action. | Frontend | P0 | Not Started | 2026-07-28 | 2026-08-10 | C-006,D-004,D-005 | 7 | Owner can view learner context and next action. | Tutor sees value beyond CRM. | V8
C-008 | P0 | Frontend Engineering | Implement fee tracker UI | Owner can see due/overdue/part-paid/paid, preview reminders, and mark paid. | Frontend | P0 | Not Started | 2026-08-01 | 2026-08-12 | C-007,D-004 | 6 | Owner identifies fee dues and sends reminder. | At least one real fee cycle tracked. | V5
E-006 | P0 | Auth, Privacy & Trust | Add inquiry consent timestamp | Store consent version/timestamp with every public inquiry and display data-use note. | Security/Backend/Frontend | P0 | Not Started | 2026-07-08 | 2026-07-18 | D-005,C-004 | 4 | Every inquiry has consent metadata. | No real data without consent trail. | V7
M-001 | P0 | QA, Testing & Release Gates | Inquiry-to-lead backend tests | Create backend tests for public inquiry capture, lead creation, and follow-up task creation. | QA/Backend | P0 | Not Started | 2026-07-18 | 2026-07-28 | D-005,D-006,C-004 | 5 | Tests pass in CI. | Workflow cannot silently break. | V2/V7
N-002 | P0 | Infrastructure & Deployment | Create staging environment | Create staging deployment mirroring production configuration and seeded demo data. | Engineering | P0 | Not Started | 2026-07-20 | 2026-08-02 | N-001,E-001,M-001 | 5 | Staging is stable and separate from production. | Guided reviews use stable URL. | V7
SEC-010 | P0 | Auth, Privacy & Trust | Implement real owner login | Replace access-code-only beta gating with real owner authentication for dashboard. | Security/Backend/Frontend | P0 | Not Started | 2026-08-01 | 2026-08-18 | E-001,N-002 | 8 | Owner dashboard requires authenticated owner. | Private user data is not public. | V7
SEC-011 | P0 | Auth, Privacy & Trust | Implement operator/admin login | Protect setup and operator console with role-specific authentication. | Security/Backend/Frontend | P0 | Not Started | 2026-08-08 | 2026-08-22 | SEC-010 | 6 | Operator tools are not publicly accessible. | No external user can access setup console. | V7
SEC-012 | P0 | Auth, Privacy & Trust | Role-based access control | Implement roles for owner, operator, admin, support with least privilege. | Security/Backend | P0 | Not Started | 2026-08-15 | 2026-08-30 | SEC-011,D-002 | 7 | Permissions are enforced across APIs. | Cross-role tests pass. | V7
SEC-013 | P0 | Auth, Privacy & Trust | Privacy policy and beta terms review | Prepare privacy policy, beta terms, data deletion promise, no guarantee claims, minor data caution. | Security/Product | P0 | Not Started | 2026-08-15 | 2026-08-31 | E-006,IMD-005 | 4 | Docs are reviewed and linked from beta. | Users understand data and scope. | V7
SEC-014 | P0 | Auth, Privacy & Trust | Data deletion workflow | Create manual/admin deletion or anonymization process for parent/student records. | Security/Backend/OPS | P0 | Not Started | 2026-08-22 | 2026-09-04 | SEC-012,SEC-013 | 5 | Deletion request can be fulfilled and logged. | User data control exists. | V7
INFRA-010 | P0 | Infrastructure & Deployment | Configure backups and restore test | Automate database backups and run at least one restore test. | Engineering/Security | P0 | Not Started | 2026-08-22 | 2026-09-04 | N-002 | 5 | Backup policy and restore evidence exist. | No real beta without recoverability. | V7
INFRA-011 | P0 | Infrastructure & Deployment | Configure logs and error monitoring | Capture backend/frontend errors and uptime alerts for beta. | Engineering | P0 | Not Started | 2026-08-22 | 2026-09-04 | N-002 | 4 | Errors are visible and triageable. | Support can respond to issues. | V7
QA-010 | P0 | QA, Testing & Release Gates | Responsive visual QA matrix | Check core screens at mobile and desktop widths and record defects. | QA/UX | P0 | Not Started | 2026-08-20 | 2026-09-06 | C-003,C-004,C-005,C-008 | 5 | Screens pass 360, 390, 768, 1024, 1440 widths. | No text overlap or broken mobile layout. | V1/V7
QA-011 | P0 | QA, Testing & Release Gates | Private beta release gate review | Run full private beta blocker checklist before inviting real users. | QA/Product | P0 | Not Started | 2026-09-01 | 2026-09-06 | SEC-014,INFRA-010,INFRA-011,QA-010 | 3 | Gate passes or blockers are documented. | Real users are not invited prematurely. | V7
GTM-001 | P1 | Marketing, Sales & Launch | Define Launch Pack offer | Define setup scope, price, deliverables, exclusions, and support level. | Founder/GTM | P0 | Not Started | 2026-09-07 | 2026-09-14 | IMD-005,QA-011 | 3 | Offer is simple and sellable. | Tutors can understand why to pay. | V1/V7
GTM-002 | P1 | Marketing, Sales & Launch | Define Monthly Assist Pack | Define monthly value around updates, dashboard, fee/follow-up support, proof/referral prompts. | Founder/GTM | P1 | Not Started | 2026-09-10 | 2026-09-18 | GTM-001 | 3 | Monthly pack has clear recurring value. | Tutor can explain why subscription continues. | V7
GTM-003 | P1 | Marketing, Sales & Launch | Create sales demo script | Create 12-minute demo showing page, inquiry, trial, WhatsApp, fee, proof, dashboard. | Founder/GTM | P0 | Not Started | 2026-09-15 | 2026-09-24 | GTM-001,C-005,C-008 | 3 | Demo script is repeatable. | Prospect understands product without roadmap lecture. | V1/V7
OPS-001 | P1 | Operator Setup & Support | Operator setup console V1 | Implement setup checklist, readiness score, blockers, missing proof, template readiness. | OPS/Frontend/Backend | P1 | Not Started | 2026-09-15 | 2026-10-10 | C-003,C-004,F-003 | 8 | Operator can set up second tutor in under 90 minutes. | Assisted setup becomes repeatable. | V1/V7
DATA-001 | P1 | Analytics & Metrics | Source tracking dashboard | Show which source creates inquiries and which converts to trial/enrollment. | Data/Frontend | P1 | Not Started | 2026-09-22 | 2026-10-15 | DATA-000,C-006 | 6 | Owner sees source-wise lead quality. | Tutor changes marketing behavior. | V7
DATA-000 | P0 | Analytics & Metrics | Define event taxonomy | Define page view, CTA click, inquiry, trial, fee, message, proof, setup, owner action events. | Data/Product | P0 | Not Started | 2026-07-08 | 2026-07-18 | A-004,A-005 | 4 | Events have trigger, properties, privacy level, owner. | Activation funnel can be measured. | V7
DATA-002 | P1 | Analytics & Metrics | Weekly owner digest | Create weekly digest of inquiries, trials, fees, proof prompts, and next actions. | Data/Backend/Frontend | P1 | Not Started | 2026-10-01 | 2026-10-25 | DATA-000,C-005,C-008 | 6 | Digest is actionable and concise. | Tutors check weekly. | V7
FE-020 | P1 | Frontend Engineering | Testimonial request workflow | Request, review, approve, hide, and publish testimonials/improvement stories. | Frontend/Backend | P1 | Not Started | 2026-10-08 | 2026-11-01 | C-003,F-003 | 6 | Proof request loop exists. | Tutor collects new proof. | V6
FE-021 | P1 | Frontend Engineering | Referral request workflow | Request referrals after positive milestone, result, trial, or monthly progress. | Frontend/Backend | P1 | Not Started | 2026-10-15 | 2026-11-08 | FE-020,F-003 | 5 | Referral prompts are available and trackable. | First referral request sent. | V6
GTM-004 | P1 | Marketing, Sales & Launch | Close first 10 paid pilots | Convert beta and warm prospects into paid pilot accounts. | Founder/GTM | P0 | Not Started | 2026-11-01 | 2026-12-13 | GTM-003,OPS-001,DATA-002 | 8 | 10 paid pilots or equivalent signed commitments. | Revenue signal validated. | V7
GTM-005 | P1 | Marketing, Sales & Launch | Create 3 case studies | Create before/after workflow proof from paid pilots. | Founder/GTM | P1 | Not Started | 2026-11-15 | 2026-12-31 | GTM-004,DATA-002 | 5 | Case studies include metrics, screenshots, quote, problem, outcome. | Proof supports public launch. | V6/V7
INFRA-020 | P1 | Infrastructure & Deployment | Production environment | Create production environment with domain, HTTPS, database, backups, monitoring, rollback. | Engineering | P1 | Not Started | 2026-12-14 | 2027-01-15 | GTM-004,INFRA-010,INFRA-011 | 8 | Production deployment is stable and recoverable. | Public launch can proceed. | V7
FE-030 | P1 | Frontend Engineering | Self-serve onboarding V1 | Allow tutor to create/complete profile with assisted fallback. | Frontend/Backend | P1 | Not Started | 2027-01-01 | 2027-01-31 | OPS-001,SEC-010 | 8 | Tutor reaches first value without full manual setup. | First value under 30 minutes. | V1/V7
GTM-010 | P1 | Marketing, Sales & Launch | Public landing and pricing page | Publish ContexureEarth Tutor landing page, pricing, demo, FAQ, case studies, privacy. | Founder/GTM/Frontend | P1 | Not Started | 2027-01-15 | 2027-02-10 | GTM-005,INFRA-020 | 5 | Landing page explains offer and converts demo interest. | Demo requests begin. | V1/V7
OPS-010 | P1 | Operator Setup & Support | Support help center | Create user docs for setup, inquiry, WhatsApp, fees, proof, privacy, troubleshooting. | Support/OPS | P1 | Not Started | 2027-01-20 | 2027-02-15 | OPS-001 | 4 | Help center covers common tasks. | Support time per account reduces. | V7
DATA-010 | P1 | Analytics & Metrics | Activation and retention dashboard | Track setup, share, inquiry, action completion, fee usage, retention, churn, support burden. | Data/Product | P1 | Not Started | 2027-02-01 | 2027-02-28 | DATA-002,INFRA-020 | 6 | Founder can review activation weekly. | Roadmap decisions use real data. | V7
QA-020 | P1 | QA, Testing & Release Gates | Public launch QA gate | Run production monitoring, privacy, deletion, onboarding, billing, conversion, mobile, rollback checks. | QA/Product | P1 | Not Started | 2027-02-15 | 2027-03-07 | INFRA-020,FE-030,GTM-010,DATA-010 | 5 | Public launch checklist passes. | No P0 blocker before campaign. | V7
GTM-011 | P1 | Marketing, Sales & Launch | Controlled public launch campaign | Launch to academic tutors and small coaching centers with content, demos, referrals, case studies. | Founder/GTM | P1 | Not Started | 2027-03-01 | 2027-03-14 | QA-020,GTM-010 | 6 | Campaign assets go live. | 50 paying customers or strong pipeline. | V1/V7
FE-040 | P2 | Frontend Engineering | Batch capacity and waitlist | Add batch seats, filling/full/waitlist states, and trial-fit routing. | Frontend/Backend | P2 | Not Started | 2027-03-15 | 2027-04-15 | GTM-011 | 6 | Batch availability informs owner actions. | Tutors avoid overbooking. | V4/V7
FE-041 | P2 | Frontend Engineering | Attendance-lite | Track class attendance and trigger absence/makeup prompts. | Frontend/Backend | P2 | Not Started | 2027-04-01 | 2027-05-01 | FE-040 | 6 | Attendance can be marked quickly by batch. | Absence follow-ups are sent. | V8
FE-042 | P2 | Frontend Engineering | Parent progress update templates | Create monthly progress update with covered topics, strengths, concerns, next focus. | Frontend/Product | P2 | Not Started | 2027-05-01 | 2027-06-15 | FE-041,F-003 | 6 | Tutor can send progress update without heavy data entry. | Progress updates improve retention. | V8
AI-001 | P2 | AI & Learning Intelligence | AI inquiry summary | Summarize inquiry into parent concern, class/board/subject, urgency, and suggested next message. | AI/Product | P2 | Not Started | 2027-04-15 | 2027-05-31 | DATA-010,C-004 | 6 | AI summary is editable and never auto-sends. | 30%+ summaries accepted/edited. | V2/V8
AI-002 | P2 | AI & Learning Intelligence | AI message drafts | Draft parent replies, fee reminders, progress notes, testimonial and referral messages with tone controls. | AI/Product | P2 | Not Started | 2027-05-15 | 2027-07-01 | AI-001,F-003 | 6 | AI drafts are safe, editable, and context-aware. | Message writing time reduces. | V3/V5/V8
DATA-020 | P2 | Analytics & Metrics | Source quality dashboard | Rank inquiry sources by volume, conversion, quality, and lost reasons. | Data/Frontend | P2 | Not Started | 2027-06-01 | 2027-07-15 | DATA-010,DATA-001 | 5 | Owner sees which channels create good inquiries. | Tutor changes marketing focus. | V7
DATA-021 | P2 | Analytics & Metrics | Monthly business review | Create monthly review of inquiries, trials, fees, proof, source quality, and next recommendations. | Data/Product | P2 | Not Started | 2027-07-01 | 2027-08-15 | DATA-020,FE-042 | 6 | Review gives concrete next actions. | Owners review monthly. | V7
STR-020 | P2 | Strategy & Product Definition | Scale segment decision | Decide whether to expand to exam coaches, hobby teachers, or double down on academic tutors. | Founder/Product | P1 | Not Started | 2027-08-15 | 2027-09-12 | DATA-021,GTM-011 | 3 | Decision memo uses retention, revenue, support, demand evidence. | Next segment chosen with evidence. | V7
AI-010 | P2 | AI & Learning Intelligence | Learner Context Card V1 | Add context card: class, board, concern, confidence, language comfort, parent goal, next tutor action. | AI/Product/Frontend | P2 | Not Started | 2027-09-13 | 2027-11-01 | FE-042,STR-020 | 8 | Context card is editable, gentle, and non-judgmental. | Tutors use it in parent conversations. | V8
SEC-020 | P2 | Auth, Privacy & Trust | Learning analytics safety policy | Define consent, correction, deletion, non-labeling, visibility, confidence and human-confirmation rules. | Security/Product | P2 | Not Started | 2027-09-13 | 2027-10-15 | AI-010 | 5 | Safety policy governs all learner analytics. | No harmful fixed labels. | V8
AI-011 | P2 | AI & Learning Intelligence | Intervention action recommendations | Suggest tutor-confirmed next actions based on attendance, concerns, goals, and progress notes. | AI/Product | P2 | Not Started | 2027-11-01 | 2027-12-31 | AI-010,SEC-020 | 7 | Recommendations are explainable and editable. | Interventions completed. | V8
AI-012 | P2 | AI & Learning Intelligence | Practical learning prompts | Generate real-world examples and small projects linked to subject, learner context, local life, planet, and careers. | AI/Product | P2 | Not Started | 2028-01-01 | 2028-03-12 | AI-011 | 7 | Prompts connect concepts to practical life. | Tutors use prompts in lessons. | V9
INST-001 | P2 | Institution Expansion | Institution ICP research | Research schools/colleges/institutes needing learner support analytics and parent communication intelligence. | Founder/Product | P2 | Not Started | 2028-03-13 | 2028-06-30 | AI-012 | 5 | Institution pain map and buying process documented. | 3 institution discovery calls completed. | V10
INST-002 | P2 | Institution Expansion | Multi-teacher account model | Add roles for owner, teacher, coordinator, admin, support and cohort-level visibility. | Product/Backend/Security | P2 | Not Started | 2028-07-01 | 2028-10-31 | INST-001,D-002 | 8 | Role model supports institution pilot. | No cross-role data leakage. | V10
INST-003 | P2 | Institution Expansion | Cohort dashboard pilot | Build cohort progress, attendance, intervention and parent communication dashboard. | Product/Data/Frontend | P2 | Not Started | 2028-11-01 | 2029-03-31 | INST-002,AI-011 | 9 | Dashboard supports one institution pilot without ERP replacement. | Pilot admin uses weekly. | V10
INST-004 | P2 | Institution Expansion | Institution pilot launch | Launch controlled pilot with school, college, or coaching institution. | Founder/Product/GTM | P2 | Not Started | 2029-04-01 | 2029-06-30 | INST-003 | 8 | Pilot contract, success metrics, support plan, data policy signed. | Institution pilot active. | V10

## Done Inventory
Task ID | Phase | Workstream | Title | Description | Owner | Priority | Status | Start | End | Dependencies | Effort | Acceptance Criteria | Validation Signal | Vision Link | Notes
DONE-001 | D0 | Strategy & Product Definition | Learning Studio strategy created | Created Learning Studio business ontology, strategy plan, execution plan, and beta rollout readiness plan. | Founder/Product | P0 | Done | 2026-06-01 | 2026-06-06 |  | 3 | Strategy docs exist and define tutor wedge. | Learning Studio is defined as trust, trial, parent communication, and recurring-fee business. | V1/V2/V4/V5
DONE-002 | D0 | Strategy & Product Definition | First validation wedge narrowed | Narrowed initial beta wedge to Ananya Learning Studio and tutor/coach persona. | Founder/Product | P0 | Done | 2026-06-05 | 2026-06-06 | DONE-001 | 3 | Ananya is the demo anchor. | Product can be reviewed through one concrete tutor story. | V1
DONE-003 | D0 | Frontend Engineering | Parallel Beta Studio UI added | Added Beta Studio tab for tutor businesses while preserving existing prototype screens. | Frontend | P0 | Done | 2026-06-06 | 2026-06-07 | DONE-002 | 3 | Tutor-specific surface exists. | Reviewer can open Ananya Learning Studio Beta Studio. | V1/V7
DONE-004 | D0 | Frontend Engineering | Parent-ready Learning Studio surface built | Added teacher credibility, proof, course cards, trial inquiry form, parent journey, trial action queue, monthly fee actions, and FAQ. | Frontend/Product | P0 | Done | 2026-06-06 | 2026-06-07 | DONE-003 | 3 | Core tutor beta UI exists. | The demo can show parent page to fee workflow. | V1/V2/V4/V5/V6
DONE-005 | D0 | Auth, Privacy & Trust | Beta safety notes added | Added beta disclaimer, beta terms view, and inquiry consent/data-use copy. | Security/Product | P0 | Done | 2026-06-07 | 2026-06-08 | DONE-004 | 3 | Beta users see scope and data-use notes. | No real-data review without safety copy. | V7
DONE-006 | D0 | Backend & Data Model | Ananya seed data enriched | Aligned backend demo seed data with richer Learning Studio story, persona statuses, and message templates. | Backend/Product | P0 | Done | 2026-06-07 | 2026-06-08 | DONE-004 | 3 | Seed data supports realistic demo. | Ananya data includes courses, proof, FAQs, leads, payments. | V1/V2/V5
DONE-007 | D0 | Auth, Privacy & Trust | Private beta access controls added | Added optional frontend access code, backend API key gate, environment examples, and production-safe settings hooks. | Security/Backend/Frontend | P0 | Done | 2026-06-08 | 2026-06-09 | DONE-005 | 3 | Beta access can be restricted. | Demo can be shared with selected reviewers only. | V7
DONE-008 | D0 | Infrastructure & Deployment | Deployment blueprint prepared | Added Postgres support, Gunicorn, static root, render.yaml, health endpoint, and deployment docs. | Engineering | P0 | Done | 2026-06-09 | 2026-06-10 | DONE-007 | 3 | Render deployment path exists. | Backend health endpoint available. | V7
DONE-009 | D0 | Infrastructure & Deployment | GitHub Actions CI added | Added frontend build and backend checks on main. | Engineering/QA | P0 | Done | 2026-06-10 | 2026-06-10 | DONE-008 | 3 | CI workflow exists. | Build/check pipeline can run on main. | V7
DONE-010 | D0 | Infrastructure & Deployment | GitHub Pages preview workflow added | Added no-new-cloud-account frontend preview path for UI-only guided review. | Engineering | P1 | Done | 2026-06-10 | 2026-06-10 | DONE-009 | 3 | Preview workflow and guide exist. | UI can be reviewed without backend hosting. | V1
DONE-011 | D0 | Documentation & Handoff | Root README updated | Updated README with BizzNexx product shape, Learning Studio beta, run commands, and deployment paths. | Documentation | P0 | Done | 2026-06-10 | 2026-06-11 | DONE-008 | 3 | README gives clear project entry. | New reviewer can understand current status. | V7
DONE-012 | D0 | Operator Setup & Support | Beta review guide created | Created guided review script for tutor beta reviews. | Operations/Product | P0 | Done | 2026-06-11 | 2026-06-11 | DONE-004 | 3 | Review guide covers parent page, inquiry, action queue, fees, and WTP. | Beta calls have a consistent script. | V1/V2/V5
DONE-013 | D0 | Operator Setup & Support | Beta feedback form created | Created structured beta feedback form with workflow fit, commercial signal, trust/safety, and product gaps. | Operations/Product | P0 | Done | 2026-06-11 | 2026-06-11 | DONE-012 | 3 | Feedback form can be used per reviewer. | WTP and product-fit signals are captured. | V7
DONE-014 | D0 | QA, Testing & Release Gates | Private beta QA checklist created | Created hosted deployment QA checks before sharing beta URL. | QA | P0 | Done | 2026-06-11 | 2026-06-12 | DONE-008 | 3 | Checklist covers HTTPS, access gate, Ananya, inquiry, message, payment, beta terms. | No beta sharing without QA pass. | V7
DONE-015 | D0 | Strategy & Product Definition | Tutor growth feature universe created | Created feature strategy, persona mapping, heatmap, ranking model, and top build order. | Product | P0 | Done | 2026-06-12 | 2026-06-12 | DONE-001 | 3 | Feature universe and ranking are documented. | MVP spine is clear. | V1-V8
DONE-016 | D0 | Strategy & Product Definition | Production accountable tasklist created | Created accountable workstreams across product, UX, FE, BE, auth, analytics, QA, infra, ops, support, GTM, and risk. | Product | P0 | Done | 2026-06-12 | 2026-06-13 | DONE-015 | 3 | Production task board exists. | Team can execute using task IDs. | V7
DONE-017 | D0 | Documentation & Handoff | Team handoff guide created | Created TEAM_HANDOFF_START_HERE.md with mission, decisions, MVP spine, first tasks, repo structure, and QA gates. | Documentation/Product | P0 | Done | 2026-06-13 | 2026-06-13 | DONE-016 | 3 | Team entry point exists. | New contributor can start from handoff guide. | V7
DONE-018 | D0 | Strategy & Product Definition | ContexureEarth vision mind map created | Created product vision mind map and renamed vision file under ContexureEarth. | Founder/Product | P1 | Done | 2026-06-13 | 2026-06-13 |  | 3 | Vision file exists under final name. | Long-term learning intelligence direction captured. | V8/V9/V10
DONE-019 | D0 | Strategy & Product Definition | ContexureEarth tutor roadmap created | Created research-backed tutor product roadmap linking BizzNexx work to ContexureEarth. | Product | P1 | Done | 2026-06-13 | 2026-06-13 | DONE-018 | 3 | Roadmap covers research, build, GTM, launch, post-launch. | Execution path is visible. | V1-V10
DONE-020 | D0 | Strategy & Product Definition | BizzNexx critical evaluation created | Evaluated what BizzNexx already achieves and how it should evolve into ContexureEarth Tutor. | Product | P1 | Done | 2026-06-13 | 2026-06-13 | DONE-019 | 3 | Evaluation gives brand architecture and product migration recommendation. | Decision: ContexureEarth public brand; BizzNexx operating engine. | V1-V10
DONE-021 | D0 | QA, Testing & Release Gates | Initial verification passed | npm run build, Django check, collectstatic dry run, compileall, and local UI response were verified previously. | Engineering/QA | P0 | Done | 2026-06-10 | 2026-06-13 | DONE-009 | 3 | Verification evidence recorded in project log. | Prototype is stable enough for deployment prep. | V7
DONE-022 | D0 | Marketing, Sales & Launch | Code pushed to GitHub | Project log records code pushed with key commits for strategy, UI, safety, deployment, and preview. | Engineering | P0 | Done | 2026-06-10 | 2026-06-13 | DONE-021 | 3 | Commits are recorded. | Remote repo has current work. | V7

## Remaining Work
Task ID | Phase | Workstream | Title | Description | Owner | Priority | Status | Start | End | Dependencies | Effort | Acceptance Criteria | Validation Signal | Vision Link | Notes
IMD-001 | P0 | Infrastructure & Deployment | Create Render Blueprint deployment | Create Render Blueprint from GitHub and let it provision frontend, backend, and Postgres database. | Engineering | P0 | Not Started | 2026-06-15 | 2026-06-17 | DONE-008,DONE-022 | 4 | Render services exist and deploy successfully. | Hosted API and frontend URLs available. | V7
IMD-002 | P0 | Auth, Privacy & Trust | Wire beta API keys | Copy backend BIZZNEXX_BETA_API_KEY to frontend VITE_BETA_API_KEY and set VITE_BETA_ACCESS_CODE. | Security/Engineering | P0 | Not Started | 2026-06-17 | 2026-06-18 | IMD-001,DONE-007 | 2 | Frontend and backend keys match; access gate works. | Unauthorized beta access blocked. | V7
IMD-003 | P0 | QA, Testing & Release Gates | Run hosted beta QA checklist | Confirm HTTPS, access gate, Ananya, Beta Studio, inquiry submit, lead creation, message preview, mark paid, beta terms. | QA/Product | P0 | Not Started | 2026-06-18 | 2026-06-20 | IMD-002,DONE-014 | 3 | QA checklist completed with pass/fail evidence. | No beta user sees broken hosted flow. | V7
IMD-004 | P0 | Research & Customer Discovery | Recruit first 5 tutor reviewers | Use existing networks to schedule guided review calls with academic tutors/coaches. | Founder/Research | P0 | Not Started | 2026-06-18 | 2026-06-24 | DONE-012,DONE-013 | 3 | 5 calls scheduled or completed. | At least 3 reviewers fit target ICP. | V1/V2/V5
IMD-005 | P0 | Research & Customer Discovery | Capture beta feedback in structured form | Use BETA_FEEDBACK_FORM for every reviewer and summarize share-worthiness, WTP, trust, and gaps. | Research/Product | P0 | Not Started | 2026-06-20 | 2026-06-28 | IMD-003,IMD-004 | 3 | Each review has completed feedback form. | Evidence informs next sprint. | V7
IMD-006 | P0 | Strategy & Product Definition | Founder decision: brand architecture | Confirm whether public brand is ContexureEarth Tutor with BizzNexx as internal/legacy engine. | Founder | P0 | Not Started | 2026-06-20 | 2026-06-22 | DONE-020 | 2 | Decision recorded in roadmap and handoff docs. | No confusion in UI/demo language. | V1-V10
IMD-007 | P0 | UX, Design & Copy | UI copy pass for ContexureEarth Tutor | Replace generic microbusiness language in tutor path with learner, parent, course, batch, fee cycle, operating rhythm. | UX/Product | P0 | Not Started | 2026-06-22 | 2026-06-27 | IMD-006,FE-001 | 4 | Tutor demo uses education-native language. | Reviewers do not perceive it as generic CRM. | V1/V8
C-001 | P0 | Frontend Engineering | Audit current frontend architecture | Identify routes, state, API usage, design debt, responsive gaps, and what can be reused. | Frontend | P0 | Not Started | 2026-06-15 | 2026-06-18 | DONE-004 | 4 | Frontend audit is documented. | Large implementation changes have a clear base. | V7
D-001 | P0 | Backend & Data Model | Audit backend models/APIs | Identify model gaps, workflow gaps, auth gaps, migration risks, and generic-to-education naming pressure. | Backend | P0 | Not Started | 2026-06-15 | 2026-06-18 | DONE-006 | 4 | Backend audit is documented. | Tenant/auth/model decisions can be made. | V7/V8
A-001 | P0 | Strategy & Product Definition | Define production personas | Document academic tutor, exam coach, hobby teacher, skill trainer, fitness trainer, corporate trainer, and priority order. | Product | P0 | Not Started | 2026-06-15 | 2026-06-17 | DONE-015 | 2 | Persona definitions are approved. | P-AST remains first ICP unless evidence changes. | V1
A-004 | P0 | Strategy & Product Definition | Map public visitor journey | Map parent path from shared link to inquiry, trial CTA, confirmation, and WhatsApp handoff. | Product/UX | P0 | Not Started | 2026-06-17 | 2026-06-20 | A-001 | 3 | Journey includes trust, course fit, fee clarity, trial, and privacy. | Parent can understand next step in 30 seconds. | V1/V2
A-005 | P0 | Strategy & Product Definition | Map owner inquiry-to-fee journey | Map owner path from inquiry to trial to enrollment to fee tracking and proof/referral prompt. | Product/UX | P0 | Not Started | 2026-06-17 | 2026-06-21 | A-001 | 3 | Every owner step has status, next action, and message template. | Owner knows what to do today. | V2/V4/V5/V6/V7
D-002 | P0 | Backend & Data Model | Define tenant/account model | Decide account, owner, operator, support, tutor studio boundaries and data isolation rules. | Backend/Security | P0 | Not Started | 2026-06-19 | 2026-06-24 | D-001 | 5 | Multi-tutor data isolation is designed. | No real beta without tenant boundary. | V7
E-001 | P0 | Auth, Privacy & Trust | Choose production auth approach | Choose email/password, OTP, managed auth, or phased approach for owner/operator dashboard. | Security/Backend | P0 | Not Started | 2026-06-22 | 2026-06-26 | D-002 | 4 | Auth decision covers roles, recovery, beta path, and production migration. | Owner dashboard protected. | V7
N-001 | P0 | Infrastructure & Deployment | Choose production hosting architecture | Decide staging/production deployment, database, static assets, backups, monitoring, domain, rollback. | Engineering | P0 | Not Started | 2026-06-22 | 2026-06-27 | D-001,E-001 | 4 | Hosting architecture is approved. | Staging can be created confidently. | V7
B-001 | P0 | UX, Design & Copy | Define ContexureEarth Tutor visual direction | Set calm, credible, parent-friendly, mobile-first, education-native design principles. | UX | P0 | Not Started | 2026-06-19 | 2026-06-23 | IMD-006 | 3 | Moodboard/design principles approved. | Tutor would not be embarrassed to share page. | V1
B-002 | P0 | UX, Design & Copy | Responsive layout system | Define layout system for public page, owner dashboard, and operator console across mobile/desktop widths. | UX/Frontend | P0 | Not Started | 2026-06-24 | 2026-07-01 | B-001,C-001 | 5 | Layouts work at 360, 390, 768, 1024, 1440 widths. | No text overlap or awkward wrapping. | V1/V7
D-004 | P0 | Backend & Data Model | Define Course/Batch model | Define course, batch, schedule, capacity, fee policy, board/class/subject fields. | Backend/Product | P0 | Not Started | 2026-06-25 | 2026-07-02 | D-002,A-005 | 5 | Model supports academic tutor MVP and future exam/hobby variants. | Course cards can be API-backed. | V1/V2
D-005 | P0 | Backend & Data Model | Define Inquiry model | Define structured parent inquiry with academic context, consent, source, duplicate detection path. | Backend/Product | P0 | Not Started | 2026-06-25 | 2026-07-02 | D-002,A-004 | 5 | Inquiry stores class, board, subject, concern, timing, trial interest, source. | Owner avoids repeated basic questions. | V2
D-006 | P0 | Backend & Data Model | Define Lead/Trial states | Define parent inquiry, contacted, trial proposed, scheduled, attended, no-show, enrolled, lost, follow-later states. | Backend/Product | P0 | Not Started | 2026-06-28 | 2026-07-05 | D-005,A-005 | 5 | States cover inquiry-to-enrollment journey. | Trial outcomes are measurable. | V4
F-003 | P0 | WhatsApp & Messaging | Create WhatsApp template library | Create first response, trial options, trial reminder, post-trial, fee reminder, progress, proof, referral messages. | Product/Copy | P0 | Not Started | 2026-06-28 | 2026-07-04 | A-005,IMD-005 | 4 | Templates are polite, editable, parent-safe, context-aware. | Tutors say tone feels natural. | V3/V4/V5/V6
C-003 | P0 | Frontend Engineering | Implement public studio page route | Productionize share-ready public page from API-backed tutor profile, courses, proof, FAQ, and CTA. | Frontend | P0 | Not Started | 2026-07-01 | 2026-07-12 | B-002,D-004 | 7 | Page renders loading, error, fallback, and published states. | Tutor says they would share page. | V1
C-004 | P0 | Frontend Engineering | Implement tutor inquiry flow | Create mobile-friendly inquiry form and confirmation state with consent and source tracking. | Frontend | P0 | Not Started | 2026-07-08 | 2026-07-18 | C-003,D-005 | 6 | Inquiry submits successfully and creates backend lead. | Parent knows what happens next. | V2
F-001 | P0 | WhatsApp & Messaging | Implement manual WhatsApp click-to-chat | Open WhatsApp with prefilled context from inquiry/trial/fee action and copy fallback. | Frontend | P0 | Not Started | 2026-07-12 | 2026-07-20 | C-004,F-003 | 5 | Owner can open/edit/copy WhatsApp messages. | Manual handoff works before API automation. | V3
C-005 | P0 | Frontend Engineering | Implement owner Today dashboard | Create action queue for new inquiries, trials, fee dues, overdue payments, proof/referral prompts. | Frontend | P0 | Not Started | 2026-07-14 | 2026-07-25 | A-005,D-006,F-001 | 7 | Owner sees actionable cards and can update statuses. | Owner knows what needs attention in under 30 seconds. | V7
C-006 | P0 | Frontend Engineering | Implement leads and trial workflow UI | Owner can move inquiry through contacted, trial, enrolled, lost, follow-later states. | Frontend | P0 | Not Started | 2026-07-22 | 2026-08-02 | C-005,D-006 | 6 | Owner can update trial statuses without confusion. | Trial queue has no stale invisible leads. | V4
C-007 | P0 | Frontend Engineering | Implement student/learner memory UI | Show lightweight learner profile and notes connected to inquiry, enrollment, parent contact, next action. | Frontend | P0 | Not Started | 2026-07-28 | 2026-08-10 | C-006,D-004,D-005 | 7 | Owner can view learner context and next action. | Tutor sees value beyond CRM. | V8
C-008 | P0 | Frontend Engineering | Implement fee tracker UI | Owner can see due/overdue/part-paid/paid, preview reminders, and mark paid. | Frontend | P0 | Not Started | 2026-08-01 | 2026-08-12 | C-007,D-004 | 6 | Owner identifies fee dues and sends reminder. | At least one real fee cycle tracked. | V5
E-006 | P0 | Auth, Privacy & Trust | Add inquiry consent timestamp | Store consent version/timestamp with every public inquiry and display data-use note. | Security/Backend/Frontend | P0 | Not Started | 2026-07-08 | 2026-07-18 | D-005,C-004 | 4 | Every inquiry has consent metadata. | No real data without consent trail. | V7
M-001 | P0 | QA, Testing & Release Gates | Inquiry-to-lead backend tests | Create backend tests for public inquiry capture, lead creation, and follow-up task creation. | QA/Backend | P0 | Not Started | 2026-07-18 | 2026-07-28 | D-005,D-006,C-004 | 5 | Tests pass in CI. | Workflow cannot silently break. | V2/V7
N-002 | P0 | Infrastructure & Deployment | Create staging environment | Create staging deployment mirroring production configuration and seeded demo data. | Engineering | P0 | Not Started | 2026-07-20 | 2026-08-02 | N-001,E-001,M-001 | 5 | Staging is stable and separate from production. | Guided reviews use stable URL. | V7
SEC-010 | P0 | Auth, Privacy & Trust | Implement real owner login | Replace access-code-only beta gating with real owner authentication for dashboard. | Security/Backend/Frontend | P0 | Not Started | 2026-08-01 | 2026-08-18 | E-001,N-002 | 8 | Owner dashboard requires authenticated owner. | Private user data is not public. | V7
SEC-011 | P0 | Auth, Privacy & Trust | Implement operator/admin login | Protect setup and operator console with role-specific authentication. | Security/Backend/Frontend | P0 | Not Started | 2026-08-08 | 2026-08-22 | SEC-010 | 6 | Operator tools are not publicly accessible. | No external user can access setup console. | V7
SEC-012 | P0 | Auth, Privacy & Trust | Role-based access control | Implement roles for owner, operator, admin, support with least privilege. | Security/Backend | P0 | Not Started | 2026-08-15 | 2026-08-30 | SEC-011,D-002 | 7 | Permissions are enforced across APIs. | Cross-role tests pass. | V7
SEC-013 | P0 | Auth, Privacy & Trust | Privacy policy and beta terms review | Prepare privacy policy, beta terms, data deletion promise, no guarantee claims, minor data caution. | Security/Product | P0 | Not Started | 2026-08-15 | 2026-08-31 | E-006,IMD-005 | 4 | Docs are reviewed and linked from beta. | Users understand data and scope. | V7
SEC-014 | P0 | Auth, Privacy & Trust | Data deletion workflow | Create manual/admin deletion or anonymization process for parent/student records. | Security/Backend/OPS | P0 | Not Started | 2026-08-22 | 2026-09-04 | SEC-012,SEC-013 | 5 | Deletion request can be fulfilled and logged. | User data control exists. | V7
INFRA-010 | P0 | Infrastructure & Deployment | Configure backups and restore test | Automate database backups and run at least one restore test. | Engineering/Security | P0 | Not Started | 2026-08-22 | 2026-09-04 | N-002 | 5 | Backup policy and restore evidence exist. | No real beta without recoverability. | V7
INFRA-011 | P0 | Infrastructure & Deployment | Configure logs and error monitoring | Capture backend/frontend errors and uptime alerts for beta. | Engineering | P0 | Not Started | 2026-08-22 | 2026-09-04 | N-002 | 4 | Errors are visible and triageable. | Support can respond to issues. | V7
QA-010 | P0 | QA, Testing & Release Gates | Responsive visual QA matrix | Check core screens at mobile and desktop widths and record defects. | QA/UX | P0 | Not Started | 2026-08-20 | 2026-09-06 | C-003,C-004,C-005,C-008 | 5 | Screens pass 360, 390, 768, 1024, 1440 widths. | No text overlap or broken mobile layout. | V1/V7
QA-011 | P0 | QA, Testing & Release Gates | Private beta release gate review | Run full private beta blocker checklist before inviting real users. | QA/Product | P0 | Not Started | 2026-09-01 | 2026-09-06 | SEC-014,INFRA-010,INFRA-011,QA-010 | 3 | Gate passes or blockers are documented. | Real users are not invited prematurely. | V7
GTM-001 | P1 | Marketing, Sales & Launch | Define Launch Pack offer | Define setup scope, price, deliverables, exclusions, and support level. | Founder/GTM | P0 | Not Started | 2026-09-07 | 2026-09-14 | IMD-005,QA-011 | 3 | Offer is simple and sellable. | Tutors can understand why to pay. | V1/V7
GTM-002 | P1 | Marketing, Sales & Launch | Define Monthly Assist Pack | Define monthly value around updates, dashboard, fee/follow-up support, proof/referral prompts. | Founder/GTM | P1 | Not Started | 2026-09-10 | 2026-09-18 | GTM-001 | 3 | Monthly pack has clear recurring value. | Tutor can explain why subscription continues. | V7
GTM-003 | P1 | Marketing, Sales & Launch | Create sales demo script | Create 12-minute demo showing page, inquiry, trial, WhatsApp, fee, proof, dashboard. | Founder/GTM | P0 | Not Started | 2026-09-15 | 2026-09-24 | GTM-001,C-005,C-008 | 3 | Demo script is repeatable. | Prospect understands product without roadmap lecture. | V1/V7
OPS-001 | P1 | Operator Setup & Support | Operator setup console V1 | Implement setup checklist, readiness score, blockers, missing proof, template readiness. | OPS/Frontend/Backend | P1 | Not Started | 2026-09-15 | 2026-10-10 | C-003,C-004,F-003 | 8 | Operator can set up second tutor in under 90 minutes. | Assisted setup becomes repeatable. | V1/V7
DATA-001 | P1 | Analytics & Metrics | Source tracking dashboard | Show which source creates inquiries and which converts to trial/enrollment. | Data/Frontend | P1 | Not Started | 2026-09-22 | 2026-10-15 | DATA-000,C-006 | 6 | Owner sees source-wise lead quality. | Tutor changes marketing behavior. | V7
DATA-000 | P0 | Analytics & Metrics | Define event taxonomy | Define page view, CTA click, inquiry, trial, fee, message, proof, setup, owner action events. | Data/Product | P0 | Not Started | 2026-07-08 | 2026-07-18 | A-004,A-005 | 4 | Events have trigger, properties, privacy level, owner. | Activation funnel can be measured. | V7
DATA-002 | P1 | Analytics & Metrics | Weekly owner digest | Create weekly digest of inquiries, trials, fees, proof prompts, and next actions. | Data/Backend/Frontend | P1 | Not Started | 2026-10-01 | 2026-10-25 | DATA-000,C-005,C-008 | 6 | Digest is actionable and concise. | Tutors check weekly. | V7
FE-020 | P1 | Frontend Engineering | Testimonial request workflow | Request, review, approve, hide, and publish testimonials/improvement stories. | Frontend/Backend | P1 | Not Started | 2026-10-08 | 2026-11-01 | C-003,F-003 | 6 | Proof request loop exists. | Tutor collects new proof. | V6
FE-021 | P1 | Frontend Engineering | Referral request workflow | Request referrals after positive milestone, result, trial, or monthly progress. | Frontend/Backend | P1 | Not Started | 2026-10-15 | 2026-11-08 | FE-020,F-003 | 5 | Referral prompts are available and trackable. | First referral request sent. | V6
GTM-004 | P1 | Marketing, Sales & Launch | Close first 10 paid pilots | Convert beta and warm prospects into paid pilot accounts. | Founder/GTM | P0 | Not Started | 2026-11-01 | 2026-12-13 | GTM-003,OPS-001,DATA-002 | 8 | 10 paid pilots or equivalent signed commitments. | Revenue signal validated. | V7
GTM-005 | P1 | Marketing, Sales & Launch | Create 3 case studies | Create before/after workflow proof from paid pilots. | Founder/GTM | P1 | Not Started | 2026-11-15 | 2026-12-31 | GTM-004,DATA-002 | 5 | Case studies include metrics, screenshots, quote, problem, outcome. | Proof supports public launch. | V6/V7
INFRA-020 | P1 | Infrastructure & Deployment | Production environment | Create production environment with domain, HTTPS, database, backups, monitoring, rollback. | Engineering | P1 | Not Started | 2026-12-14 | 2027-01-15 | GTM-004,INFRA-010,INFRA-011 | 8 | Production deployment is stable and recoverable. | Public launch can proceed. | V7
FE-030 | P1 | Frontend Engineering | Self-serve onboarding V1 | Allow tutor to create/complete profile with assisted fallback. | Frontend/Backend | P1 | Not Started | 2027-01-01 | 2027-01-31 | OPS-001,SEC-010 | 8 | Tutor reaches first value without full manual setup. | First value under 30 minutes. | V1/V7
GTM-010 | P1 | Marketing, Sales & Launch | Public landing and pricing page | Publish ContexureEarth Tutor landing page, pricing, demo, FAQ, case studies, privacy. | Founder/GTM/Frontend | P1 | Not Started | 2027-01-15 | 2027-02-10 | GTM-005,INFRA-020 | 5 | Landing page explains offer and converts demo interest. | Demo requests begin. | V1/V7
OPS-010 | P1 | Operator Setup & Support | Support help center | Create user docs for setup, inquiry, WhatsApp, fees, proof, privacy, troubleshooting. | Support/OPS | P1 | Not Started | 2027-01-20 | 2027-02-15 | OPS-001 | 4 | Help center covers common tasks. | Support time per account reduces. | V7
DATA-010 | P1 | Analytics & Metrics | Activation and retention dashboard | Track setup, share, inquiry, action completion, fee usage, retention, churn, support burden. | Data/Product | P1 | Not Started | 2027-02-01 | 2027-02-28 | DATA-002,INFRA-020 | 6 | Founder can review activation weekly. | Roadmap decisions use real data. | V7
QA-020 | P1 | QA, Testing & Release Gates | Public launch QA gate | Run production monitoring, privacy, deletion, onboarding, billing, conversion, mobile, rollback checks. | QA/Product | P1 | Not Started | 2027-02-15 | 2027-03-07 | INFRA-020,FE-030,GTM-010,DATA-010 | 5 | Public launch checklist passes. | No P0 blocker before campaign. | V7
GTM-011 | P1 | Marketing, Sales & Launch | Controlled public launch campaign | Launch to academic tutors and small coaching centers with content, demos, referrals, case studies. | Founder/GTM | P1 | Not Started | 2027-03-01 | 2027-03-14 | QA-020,GTM-010 | 6 | Campaign assets go live. | 50 paying customers or strong pipeline. | V1/V7
FE-040 | P2 | Frontend Engineering | Batch capacity and waitlist | Add batch seats, filling/full/waitlist states, and trial-fit routing. | Frontend/Backend | P2 | Not Started | 2027-03-15 | 2027-04-15 | GTM-011 | 6 | Batch availability informs owner actions. | Tutors avoid overbooking. | V4/V7
FE-041 | P2 | Frontend Engineering | Attendance-lite | Track class attendance and trigger absence/makeup prompts. | Frontend/Backend | P2 | Not Started | 2027-04-01 | 2027-05-01 | FE-040 | 6 | Attendance can be marked quickly by batch. | Absence follow-ups are sent. | V8
FE-042 | P2 | Frontend Engineering | Parent progress update templates | Create monthly progress update with covered topics, strengths, concerns, next focus. | Frontend/Product | P2 | Not Started | 2027-05-01 | 2027-06-15 | FE-041,F-003 | 6 | Tutor can send progress update without heavy data entry. | Progress updates improve retention. | V8
AI-001 | P2 | AI & Learning Intelligence | AI inquiry summary | Summarize inquiry into parent concern, class/board/subject, urgency, and suggested next message. | AI/Product | P2 | Not Started | 2027-04-15 | 2027-05-31 | DATA-010,C-004 | 6 | AI summary is editable and never auto-sends. | 30%+ summaries accepted/edited. | V2/V8
AI-002 | P2 | AI & Learning Intelligence | AI message drafts | Draft parent replies, fee reminders, progress notes, testimonial and referral messages with tone controls. | AI/Product | P2 | Not Started | 2027-05-15 | 2027-07-01 | AI-001,F-003 | 6 | AI drafts are safe, editable, and context-aware. | Message writing time reduces. | V3/V5/V8
DATA-020 | P2 | Analytics & Metrics | Source quality dashboard | Rank inquiry sources by volume, conversion, quality, and lost reasons. | Data/Frontend | P2 | Not Started | 2027-06-01 | 2027-07-15 | DATA-010,DATA-001 | 5 | Owner sees which channels create good inquiries. | Tutor changes marketing focus. | V7
DATA-021 | P2 | Analytics & Metrics | Monthly business review | Create monthly review of inquiries, trials, fees, proof, source quality, and next recommendations. | Data/Product | P2 | Not Started | 2027-07-01 | 2027-08-15 | DATA-020,FE-042 | 6 | Review gives concrete next actions. | Owners review monthly. | V7
STR-020 | P2 | Strategy & Product Definition | Scale segment decision | Decide whether to expand to exam coaches, hobby teachers, or double down on academic tutors. | Founder/Product | P1 | Not Started | 2027-08-15 | 2027-09-12 | DATA-021,GTM-011 | 3 | Decision memo uses retention, revenue, support, demand evidence. | Next segment chosen with evidence. | V7
AI-010 | P2 | AI & Learning Intelligence | Learner Context Card V1 | Add context card: class, board, concern, confidence, language comfort, parent goal, next tutor action. | AI/Product/Frontend | P2 | Not Started | 2027-09-13 | 2027-11-01 | FE-042,STR-020 | 8 | Context card is editable, gentle, and non-judgmental. | Tutors use it in parent conversations. | V8
SEC-020 | P2 | Auth, Privacy & Trust | Learning analytics safety policy | Define consent, correction, deletion, non-labeling, visibility, confidence and human-confirmation rules. | Security/Product | P2 | Not Started | 2027-09-13 | 2027-10-15 | AI-010 | 5 | Safety policy governs all learner analytics. | No harmful fixed labels. | V8
AI-011 | P2 | AI & Learning Intelligence | Intervention action recommendations | Suggest tutor-confirmed next actions based on attendance, concerns, goals, and progress notes. | AI/Product | P2 | Not Started | 2027-11-01 | 2027-12-31 | AI-010,SEC-020 | 7 | Recommendations are explainable and editable. | Interventions completed. | V8
AI-012 | P2 | AI & Learning Intelligence | Practical learning prompts | Generate real-world examples and small projects linked to subject, learner context, local life, planet, and careers. | AI/Product | P2 | Not Started | 2028-01-01 | 2028-03-12 | AI-011 | 7 | Prompts connect concepts to practical life. | Tutors use prompts in lessons. | V9
INST-001 | P2 | Institution Expansion | Institution ICP research | Research schools/colleges/institutes needing learner support analytics and parent communication intelligence. | Founder/Product | P2 | Not Started | 2028-03-13 | 2028-06-30 | AI-012 | 5 | Institution pain map and buying process documented. | 3 institution discovery calls completed. | V10
INST-002 | P2 | Institution Expansion | Multi-teacher account model | Add roles for owner, teacher, coordinator, admin, support and cohort-level visibility. | Product/Backend/Security | P2 | Not Started | 2028-07-01 | 2028-10-31 | INST-001,D-002 | 8 | Role model supports institution pilot. | No cross-role data leakage. | V10
INST-003 | P2 | Institution Expansion | Cohort dashboard pilot | Build cohort progress, attendance, intervention and parent communication dashboard. | Product/Data/Frontend | P2 | Not Started | 2028-11-01 | 2029-03-31 | INST-002,AI-011 | 9 | Dashboard supports one institution pilot without ERP replacement. | Pilot admin uses weekly. | V10
INST-004 | P2 | Institution Expansion | Institution pilot launch | Launch controlled pilot with school, college, or coaching institution. | Founder/Product/GTM | P2 | Not Started | 2029-04-01 | 2029-06-30 | INST-003 | 8 | Pilot contract, success metrics, support plan, data policy signed. | Institution pilot active. | V10

## Vision Map
Vision ID | Pillar | Founder Belief | Product Translation | Product Surface | Validation Signal
V1 | Tutor Trust Entry | Tutors must look credible before parents inquire. | Public page, proof, FAQ, local context. | Public Trust Page | Tutor says they would share page.
V2 | Structured Context Capture | Raw WhatsApp lacks class, board, concern, timing context. | Inquiry form captures minimum useful learning/business context. | Structured Inquiry | Owner can reply without basic questions.
V3 | WhatsApp-Native Operations | Tutors will not abandon WhatsApp. | Editable click-to-chat templates and action statuses. | WhatsApp Handoff | Owner sends/records follow-ups weekly.
V4 | Trial To Enrollment Discipline | Missed demos leak revenue. | Trial status, reminders, post-trial follow-up, enrolled/lost reasons. | Trial Workflow | Trial outcomes are marked.
V5 | Fee Clarity Without Awkwardness | Recurring cash flow is relationship-sensitive. | Fee cycles, ageing, polite reminders, mark paid/part paid. | Fee Cycle | Tutor tracks at least one real cycle.
V6 | Proof And Referral Loop | Good teaching often stays invisible. | Testimonials, result proof, referral requests, approval workflow. | Proof Loop | Tutor collects proof monthly.
V7 | Owner Operating Rhythm | Dashboard must produce action, not decoration. | Today queue, weekly digest, readiness and source signals. | Operating Rhythm | Weekly completed tutor actions increase.
V8 | Learner Context | The larger vision requires understanding learners beyond marks. | Learner context card, parent goals, confidence, concerns, next action. | Learner Context Card | Tutors use context in parent conversations.
V9 | Practical Learning | Learning must connect to life, work, planet, community. | Project prompts, real-world examples, contextual lesson enrichment. | Practical Learning Engine | Assignments include real-world context.
V10 | Institutional Intelligence | Tutors are entry point to schools/colleges. | Cohort dashboards, intervention tracking, improvement reports. | Institution Dashboards | Institution pilot signed.

## Timeline
Phase ID | Phase | Start | End | Duration Days | Target Gate
D0 | Already Done / Existing BizzNexx Assets | 2026-06-01 | 2026-06-13 | 13
P0 | Foundation & Product Definition | 2026-06-15 | 2026-06-28 | 14
P1 | Concierge Prototype | 2026-06-29 | 2026-07-19 | 21 | Alpha Gate
P2 | Private Beta | 2026-07-20 | 2026-09-06 | 49 | Private Beta Gate
P3 | Paid Pilot | 2026-09-07 | 2026-12-13 | 98 | Paid Pilot Gate
P4 | Public Launch V1 | 2026-12-14 | 2027-03-14 | 91 | Public Launch Gate
P5 | Growth & Intelligence V1 | 2027-03-15 | 2027-09-12 | 182 | Intelligence Gate
P6 | Learning Context V1 | 2027-09-13 | 2028-03-12 | 182 | Learning Context Gate
P7 | Institution Expansion | 2028-03-13 | 2029-06-30 | 475 | Institution Gate

## Dependencies
Task ID | Depends On | Dependency Type | Why It Matters | Blocked If Missing
DONE-002 | DONE-001 | Finish-to-start | Task relies on upstream output being complete. | Yes
DONE-003 | DONE-002 | Finish-to-start | Task relies on upstream output being complete. | Yes
DONE-004 | DONE-003 | Finish-to-start | Task relies on upstream output being complete. | Yes
DONE-005 | DONE-004 | Finish-to-start | Task relies on upstream output being complete. | Yes
DONE-006 | DONE-004 | Finish-to-start | Task relies on upstream output being complete. | Yes
DONE-007 | DONE-005 | Finish-to-start | Task relies on upstream output being complete. | Yes
DONE-008 | DONE-007 | Finish-to-start | Task relies on upstream output being complete. | Yes
DONE-009 | DONE-008 | Finish-to-start | Task relies on upstream output being complete. | Yes
DONE-010 | DONE-009 | Finish-to-start | Task relies on upstream output being complete. | Yes
DONE-011 | DONE-008 | Finish-to-start | Task relies on upstream output being complete. | Yes
DONE-012 | DONE-004 | Finish-to-start | Task relies on upstream output being complete. | Yes
DONE-013 | DONE-012 | Finish-to-start | Task relies on upstream output being complete. | Yes
DONE-014 | DONE-008 | Finish-to-start | Task relies on upstream output being complete. | Yes
DONE-015 | DONE-001 | Finish-to-start | Task relies on upstream output being complete. | Yes
DONE-016 | DONE-015 | Finish-to-start | Task relies on upstream output being complete. | Yes
DONE-017 | DONE-016 | Finish-to-start | Task relies on upstream output being complete. | Yes
DONE-019 | DONE-018 | Finish-to-start | Task relies on upstream output being complete. | Yes
DONE-020 | DONE-019 | Finish-to-start | Task relies on upstream output being complete. | Yes
DONE-021 | DONE-009 | Finish-to-start | Task relies on upstream output being complete. | Yes
DONE-022 | DONE-021 | Finish-to-start | Task relies on upstream output being complete. | Yes
IMD-001 | DONE-008 | Finish-to-start | Task relies on upstream output being complete. | Yes
IMD-001 | DONE-022 | Finish-to-start | Task relies on upstream output being complete. | Yes
IMD-002 | IMD-001 | Finish-to-start | Task relies on upstream output being complete. | Yes
IMD-002 | DONE-007 | Finish-to-start | Task relies on upstream output being complete. | Yes
IMD-003 | IMD-002 | Finish-to-start | Task relies on upstream output being complete. | Yes
IMD-003 | DONE-014 | Finish-to-start | Task relies on upstream output being complete. | Yes
IMD-004 | DONE-012 | Finish-to-start | Task relies on upstream output being complete. | Yes
IMD-004 | DONE-013 | Finish-to-start | Task relies on upstream output being complete. | Yes
IMD-005 | IMD-003 | Finish-to-start | Task relies on upstream output being complete. | Yes
IMD-005 | IMD-004 | Finish-to-start | Task relies on upstream output being complete. | Yes
IMD-006 | DONE-020 | Finish-to-start | Task relies on upstream output being complete. | Yes
IMD-007 | IMD-006 | Finish-to-start | Task relies on upstream output being complete. | Yes
IMD-007 | FE-001 | Finish-to-start | Task relies on upstream output being complete. | Yes
C-001 | DONE-004 | Finish-to-start | Task relies on upstream output being complete. | Yes
D-001 | DONE-006 | Finish-to-start | Task relies on upstream output being complete. | Yes
A-001 | DONE-015 | Finish-to-start | Task relies on upstream output being complete. | Yes
A-004 | A-001 | Finish-to-start | Task relies on upstream output being complete. | Yes
A-005 | A-001 | Finish-to-start | Task relies on upstream output being complete. | Yes
D-002 | D-001 | Finish-to-start | Task relies on upstream output being complete. | Yes
E-001 | D-002 | Finish-to-start | Task relies on upstream output being complete. | Yes
N-001 | D-001 | Finish-to-start | Task relies on upstream output being complete. | Yes
N-001 | E-001 | Finish-to-start | Task relies on upstream output being complete. | Yes
B-001 | IMD-006 | Finish-to-start | Task relies on upstream output being complete. | Yes
B-002 | B-001 | Finish-to-start | Task relies on upstream output being complete. | Yes
B-002 | C-001 | Finish-to-start | Task relies on upstream output being complete. | Yes
D-004 | D-002 | Finish-to-start | Task relies on upstream output being complete. | Yes
D-004 | A-005 | Finish-to-start | Task relies on upstream output being complete. | Yes
D-005 | D-002 | Finish-to-start | Task relies on upstream output being complete. | Yes
D-005 | A-004 | Finish-to-start | Task relies on upstream output being complete. | Yes
D-006 | D-005 | Finish-to-start | Task relies on upstream output being complete. | Yes
D-006 | A-005 | Finish-to-start | Task relies on upstream output being complete. | Yes
F-003 | A-005 | Finish-to-start | Task relies on upstream output being complete. | Yes
F-003 | IMD-005 | Finish-to-start | Task relies on upstream output being complete. | Yes
C-003 | B-002 | Finish-to-start | Task relies on upstream output being complete. | Yes
C-003 | D-004 | Finish-to-start | Task relies on upstream output being complete. | Yes
C-004 | C-003 | Finish-to-start | Task relies on upstream output being complete. | Yes
C-004 | D-005 | Finish-to-start | Task relies on upstream output being complete. | Yes
F-001 | C-004 | Finish-to-start | Task relies on upstream output being complete. | Yes
F-001 | F-003 | Finish-to-start | Task relies on upstream output being complete. | Yes
C-005 | A-005 | Finish-to-start | Task relies on upstream output being complete. | Yes
C-005 | D-006 | Finish-to-start | Task relies on upstream output being complete. | Yes
C-005 | F-001 | Finish-to-start | Task relies on upstream output being complete. | Yes
C-006 | C-005 | Finish-to-start | Task relies on upstream output being complete. | Yes
C-006 | D-006 | Finish-to-start | Task relies on upstream output being complete. | Yes
C-007 | C-006 | Finish-to-start | Task relies on upstream output being complete. | Yes
C-007 | D-004 | Finish-to-start | Task relies on upstream output being complete. | Yes
C-007 | D-005 | Finish-to-start | Task relies on upstream output being complete. | Yes
C-008 | C-007 | Finish-to-start | Task relies on upstream output being complete. | Yes
C-008 | D-004 | Finish-to-start | Task relies on upstream output being complete. | Yes
E-006 | D-005 | Finish-to-start | Task relies on upstream output being complete. | Yes
E-006 | C-004 | Finish-to-start | Task relies on upstream output being complete. | Yes
M-001 | D-005 | Finish-to-start | Task relies on upstream output being complete. | Yes
M-001 | D-006 | Finish-to-start | Task relies on upstream output being complete. | Yes
M-001 | C-004 | Finish-to-start | Task relies on upstream output being complete. | Yes
N-002 | N-001 | Finish-to-start | Task relies on upstream output being complete. | Yes
N-002 | E-001 | Finish-to-start | Task relies on upstream output being complete. | Yes
N-002 | M-001 | Finish-to-start | Task relies on upstream output being complete. | Yes
SEC-010 | E-001 | Finish-to-start | Task relies on upstream output being complete. | Yes
SEC-010 | N-002 | Finish-to-start | Task relies on upstream output being complete. | Yes
SEC-011 | SEC-010 | Finish-to-start | Task relies on upstream output being complete. | Yes
SEC-012 | SEC-011 | Finish-to-start | Task relies on upstream output being complete. | Yes
SEC-012 | D-002 | Finish-to-start | Task relies on upstream output being complete. | Yes
SEC-013 | E-006 | Finish-to-start | Task relies on upstream output being complete. | Yes
SEC-013 | IMD-005 | Finish-to-start | Task relies on upstream output being complete. | Yes
SEC-014 | SEC-012 | Finish-to-start | Task relies on upstream output being complete. | Yes
SEC-014 | SEC-013 | Finish-to-start | Task relies on upstream output being complete. | Yes
INFRA-010 | N-002 | Finish-to-start | Task relies on upstream output being complete. | Yes
INFRA-011 | N-002 | Finish-to-start | Task relies on upstream output being complete. | Yes
QA-010 | C-003 | Finish-to-start | Task relies on upstream output being complete. | Yes
QA-010 | C-004 | Finish-to-start | Task relies on upstream output being complete. | Yes
QA-010 | C-005 | Finish-to-start | Task relies on upstream output being complete. | Yes
QA-010 | C-008 | Finish-to-start | Task relies on upstream output being complete. | Yes
QA-011 | SEC-014 | Finish-to-start | Task relies on upstream output being complete. | Yes
QA-011 | INFRA-010 | Finish-to-start | Task relies on upstream output being complete. | Yes
QA-011 | INFRA-011 | Finish-to-start | Task relies on upstream output being complete. | Yes
QA-011 | QA-010 | Finish-to-start | Task relies on upstream output being complete. | Yes
GTM-001 | IMD-005 | Finish-to-start | Task relies on upstream output being complete. | Yes
GTM-001 | QA-011 | Finish-to-start | Task relies on upstream output being complete. | Yes
GTM-002 | GTM-001 | Finish-to-start | Task relies on upstream output being complete. | Yes
GTM-003 | GTM-001 | Finish-to-start | Task relies on upstream output being complete. | Yes
GTM-003 | C-005 | Finish-to-start | Task relies on upstream output being complete. | Yes
GTM-003 | C-008 | Finish-to-start | Task relies on upstream output being complete. | Yes
OPS-001 | C-003 | Finish-to-start | Task relies on upstream output being complete. | Yes
OPS-001 | C-004 | Finish-to-start | Task relies on upstream output being complete. | Yes
OPS-001 | F-003 | Finish-to-start | Task relies on upstream output being complete. | Yes
DATA-001 | DATA-000 | Finish-to-start | Task relies on upstream output being complete. | Yes
DATA-001 | C-006 | Finish-to-start | Task relies on upstream output being complete. | Yes
DATA-000 | A-004 | Finish-to-start | Task relies on upstream output being complete. | Yes
DATA-000 | A-005 | Finish-to-start | Task relies on upstream output being complete. | Yes
DATA-002 | DATA-000 | Finish-to-start | Task relies on upstream output being complete. | Yes
DATA-002 | C-005 | Finish-to-start | Task relies on upstream output being complete. | Yes
DATA-002 | C-008 | Finish-to-start | Task relies on upstream output being complete. | Yes
FE-020 | C-003 | Finish-to-start | Task relies on upstream output being complete. | Yes
FE-020 | F-003 | Finish-to-start | Task relies on upstream output being complete. | Yes
FE-021 | FE-020 | Finish-to-start | Task relies on upstream output being complete. | Yes
FE-021 | F-003 | Finish-to-start | Task relies on upstream output being complete. | Yes
GTM-004 | GTM-003 | Finish-to-start | Task relies on upstream output being complete. | Yes
GTM-004 | OPS-001 | Finish-to-start | Task relies on upstream output being complete. | Yes
GTM-004 | DATA-002 | Finish-to-start | Task relies on upstream output being complete. | Yes
GTM-005 | GTM-004 | Finish-to-start | Task relies on upstream output being complete. | Yes
GTM-005 | DATA-002 | Finish-to-start | Task relies on upstream output being complete. | Yes
INFRA-020 | GTM-004 | Finish-to-start | Task relies on upstream output being complete. | Yes
INFRA-020 | INFRA-010 | Finish-to-start | Task relies on upstream output being complete. | Yes
INFRA-020 | INFRA-011 | Finish-to-start | Task relies on upstream output being complete. | Yes
FE-030 | OPS-001 | Finish-to-start | Task relies on upstream output being complete. | Yes
FE-030 | SEC-010 | Finish-to-start | Task relies on upstream output being complete. | Yes
GTM-010 | GTM-005 | Finish-to-start | Task relies on upstream output being complete. | Yes
GTM-010 | INFRA-020 | Finish-to-start | Task relies on upstream output being complete. | Yes
OPS-010 | OPS-001 | Finish-to-start | Task relies on upstream output being complete. | Yes
DATA-010 | DATA-002 | Finish-to-start | Task relies on upstream output being complete. | Yes
DATA-010 | INFRA-020 | Finish-to-start | Task relies on upstream output being complete. | Yes
QA-020 | INFRA-020 | Finish-to-start | Task relies on upstream output being complete. | Yes
QA-020 | FE-030 | Finish-to-start | Task relies on upstream output being complete. | Yes
QA-020 | GTM-010 | Finish-to-start | Task relies on upstream output being complete. | Yes
QA-020 | DATA-010 | Finish-to-start | Task relies on upstream output being complete. | Yes
GTM-011 | QA-020 | Finish-to-start | Task relies on upstream output being complete. | Yes
GTM-011 | GTM-010 | Finish-to-start | Task relies on upstream output being complete. | Yes
FE-040 | GTM-011 | Finish-to-start | Task relies on upstream output being complete. | Yes
FE-041 | FE-040 | Finish-to-start | Task relies on upstream output being complete. | Yes
FE-042 | FE-041 | Finish-to-start | Task relies on upstream output being complete. | Yes
FE-042 | F-003 | Finish-to-start | Task relies on upstream output being complete. | Yes
AI-001 | DATA-010 | Finish-to-start | Task relies on upstream output being complete. | Yes
AI-001 | C-004 | Finish-to-start | Task relies on upstream output being complete. | Yes
AI-002 | AI-001 | Finish-to-start | Task relies on upstream output being complete. | Yes
AI-002 | F-003 | Finish-to-start | Task relies on upstream output being complete. | Yes
DATA-020 | DATA-010 | Finish-to-start | Task relies on upstream output being complete. | Yes
DATA-020 | DATA-001 | Finish-to-start | Task relies on upstream output being complete. | Yes
DATA-021 | DATA-020 | Finish-to-start | Task relies on upstream output being complete. | Yes
DATA-021 | FE-042 | Finish-to-start | Task relies on upstream output being complete. | Yes
STR-020 | DATA-021 | Finish-to-start | Task relies on upstream output being complete. | Yes
STR-020 | GTM-011 | Finish-to-start | Task relies on upstream output being complete. | Yes
AI-010 | FE-042 | Finish-to-start | Task relies on upstream output being complete. | Yes
AI-010 | STR-020 | Finish-to-start | Task relies on upstream output being complete. | Yes
SEC-020 | AI-010 | Finish-to-start | Task relies on upstream output being complete. | Yes
AI-011 | AI-010 | Finish-to-start | Task relies on upstream output being complete. | Yes
AI-011 | SEC-020 | Finish-to-start | Task relies on upstream output being complete. | Yes
AI-012 | AI-011 | Finish-to-start | Task relies on upstream output being complete. | Yes
INST-001 | AI-012 | Finish-to-start | Task relies on upstream output being complete. | Yes
INST-002 | INST-001 | Finish-to-start | Task relies on upstream output being complete. | Yes
INST-002 | D-002 | Finish-to-start | Task relies on upstream output being complete. | Yes
INST-003 | INST-002 | Finish-to-start | Task relies on upstream output being complete. | Yes
INST-003 | AI-011 | Finish-to-start | Task relies on upstream output being complete. | Yes
INST-004 | INST-003 | Finish-to-start | Task relies on upstream output being complete. | Yes

## Launch Gates
Gate | Phase | Target Date | Criteria | Required Tasks | Status | Evidence / Notes
Alpha Gate | P1 | 2026-07-19 | Public page works; inquiry flow works; owner queue exists; WhatsApp handoff works; fee tracker exists; demo data labeled. | C-003,C-004,C-005,C-008,F-001 | Not Started
Private Beta Gate | P2 | 2026-09-06 | Owner login; tenant isolation; persistence; consent; beta terms; backup plan; smoke tests; mobile QA; support channel. | SEC-010,D-002,E-006,SEC-014,INFRA-010,QA-011 | Not Started
Paid Pilot Gate | P3 | 2026-12-13 | Repeatable setup; pricing clear; support docs; source tracking; weekly digest; proof/referral; case template. | GTM-001,OPS-001,DATA-002,FE-020,FE-021,GTM-005 | Not Started
Public Launch Gate | P4 | 2027-03-14 | Production monitoring; rollback; privacy; deletion flow; onboarding; billing; conversion dashboard; churn tracking. | INFRA-020,FE-030,GTM-010,DATA-010,QA-020 | Not Started
Intelligence Gate | P5 | 2027-09-12 | AI drafts accepted; analytics useful; support load manageable; data safety stable. | AI-001,AI-002,DATA-021,STR-020 | Not Started
Learning Context Gate | P6 | 2028-03-12 | Learner context used ethically; parent reports constructive; consent/correction ready. | AI-010,SEC-020,AI-011,AI-012 | Not Started
Institution Gate | P7 | 2029-06-30 | Tutor product retained; data privacy mature; institution pilot has signed success criteria. | INST-001,INST-002,INST-003,INST-004 | Not Started

## Risk Register
Risk ID | Risk | Impact | Likelihood | Why It Matters | Mitigation | Owner | Status | Linked Task
R-001 | Identity drift between BizzNexx and ContexureEarth | High | High | Confuses customers and roadmap. | Make ContexureEarth public education brand; BizzNexx internal/legacy engine. | Founder | Open | IMD-006
R-002 | Overbuilding LMS/ERP features | High | Medium | Slows launch and weakens wedge. | Use decision rules and P3 deferral list. | Product | Open | STR-002
R-003 | Tutor expects guaranteed leads | High | Medium | Creates mistrust and churn. | Position as conversion/operations, not marketplace. | GTM | Open | GTM-001
R-004 | Parent/student data leakage | Critical | Low | Trust and legal risk. | Tenant isolation, auth, consent, deletion, minimization. | Security | Open | D-002
R-005 | WhatsApp automation too early | Medium | Medium | Compliance and complexity risk. | Launch manual handoff first. | Product | Open | F-001
R-006 | Fee reminders feel aggressive | Medium | Medium | Relationship damage. | Polite templates and manual review before send. | UX | Open | F-003
R-007 | Weak weekly retention | High | Medium | Product becomes setup service only. | Build owner action rhythm and weekly digest. | Data/Product | Open | DATA-002
R-008 | AI overclaims learner ability | Critical | Medium | Can harm learners and trust. | Human-confirmed, editable, non-judgmental insights. | AI/Security | Open | SEC-020
R-009 | Support burden too high | Medium | Medium | Margins suffer. | Setup SOP, help center, fewer custom workflows. | OPS | Open | OPS-001
R-010 | No paid willingness | High | Medium | Business model not validated. | Paid pilot pricing tests and cancellation interviews. | GTM | Open | GTM-004

## Metrics
Metric Type | Metric | Definition | Cadence | Owner | First Relevant Phase | Target
North Star | Weekly completed tutor actions | Count inquiry replies, trial follow-ups, fee updates, reminders, proof/referral/progress actions completed weekly. | Weekly | Product/Data | P2 | 25+ actions/week across beta by private beta end
Activation | Setup completed | Tutor profile, courses, proof, FAQ, templates and public page ready. | Weekly | OPS | P1 | 70% of onboarded tutors complete setup
Activation | Public page shared | Tutor shares link with parent/prospect. | Weekly | GTM/Data | P1 | 3 of first 5 pilot tutors share page
Activation | First inquiry captured | At least one real inquiry submitted. | Weekly | Product/Data | P1 | 20 real inquiries by concierge exit
Retention | Dashboard weekly active tutors | Tutors visiting action queue weekly. | Weekly | Data | P2 | 50% private beta WAU
Workflow | Inquiry status update rate | Share of inquiries with status updated by owner. | Weekly | Data | P2 | 30%+ in private beta
Revenue | Paid pilot conversion | Beta users converting to paid pilot. | Monthly | GTM | P3 | 10 paid pilots
Revenue | Month-two retention | Paid pilots active in second month. | Monthly | GTM/Data | P3 | 60%+
Quality | Setup time | Time to create share-ready tutor account. | Monthly | OPS | P3 | Under 90 minutes
Learning | Learner context card usage | Learners with useful context card reviewed by tutor. | Monthly | AI/Data | P6 | 50% of active learners in context pilots

## Research Tracker
Research ID | Name | Segment | City | Contact | Status | Scheduled Date | Completed Date | Current Tools | Top Pain | Pain Score 1-5 | WTP Setup | WTP Monthly | Key Quote | Next Step
RCH-001 |  |  |  |  | Not Contacted
RCH-002 |  |  |  |  | Not Contacted
RCH-003 |  |  |  |  | Not Contacted
RCH-004 |  |  |  |  | Not Contacted
RCH-005 |  |  |  |  | Not Contacted
RCH-006 |  |  |  |  | Not Contacted
RCH-007 |  |  |  |  | Not Contacted
RCH-008 |  |  |  |  | Not Contacted
RCH-009 |  |  |  |  | Not Contacted
RCH-010 |  |  |  |  | Not Contacted
RCH-011 |  |  |  |  | Not Contacted
RCH-012 |  |  |  |  | Not Contacted
RCH-013 |  |  |  |  | Not Contacted
RCH-014 |  |  |  |  | Not Contacted
RCH-015 |  |  |  |  | Not Contacted
RCH-016 |  |  |  |  | Not Contacted
RCH-017 |  |  |  |  | Not Contacted
RCH-018 |  |  |  |  | Not Contacted
RCH-019 |  |  |  |  | Not Contacted
RCH-020 |  |  |  |  | Not Contacted
RCH-021 |  |  |  |  | Not Contacted
RCH-022 |  |  |  |  | Not Contacted
RCH-023 |  |  |  |  | Not Contacted
RCH-024 |  |  |  |  | Not Contacted
RCH-025 |  |  |  |  | Not Contacted
RCH-026 |  |  |  |  | Not Contacted
RCH-027 |  |  |  |  | Not Contacted
RCH-028 |  |  |  |  | Not Contacted
RCH-029 |  |  |  |  | Not Contacted
RCH-030 |  |  |  |  | Not Contacted
RCH-031 |  |  |  |  | Not Contacted
RCH-032 |  |  |  |  | Not Contacted
RCH-033 |  |  |  |  | Not Contacted
RCH-034 |  |  |  |  | Not Contacted
RCH-035 |  |  |  |  | Not Contacted
RCH-036 |  |  |  |  | Not Contacted
RCH-037 |  |  |  |  | Not Contacted
RCH-038 |  |  |  |  | Not Contacted
RCH-039 |  |  |  |  | Not Contacted
RCH-040 |  |  |  |  | Not Contacted

## Backlog
Backlog ID | Item | Priority | Category | Why It Exists | Trigger To Build | Notes
BKL-001 | Google Forms import | P2 | Scale | Useful for tutors already using Forms. | After native inquiry validates.
BKL-002 | Google Sheets export | P2 | Scale | Useful for trust and data portability. | After paid pilot.
BKL-003 | Payment gateway | P3 | Deferred | Adds complexity before manual fee value proven. | After fee tracker retention.
BKL-004 | Parent mobile app | P3 | Deferred | Too much scope before owner workflow retention. | After institution/tutor demand.
BKL-005 | Full LMS | P3 | Deferred | Competes with LMS and dilutes wedge. | Only if paid users demand.
BKL-006 | WhatsApp Cloud API automation | P2/P3 | Scale | Useful after manual workflow proves value and opt-in is clear. | After 100+ active tutors.
BKL-007 | Corporate trainer proposal workflow | P3 | Deferred | Different ICP and sales cycle. | After tutor engine matures.
BKL-008 | Full test engine | P3 | Deferred | Exam-coach specific and data-heavy. | After exam coach segment validated.

## Summary Data (hidden)
Status | Count
Done | 22
In Progress | 0
In Review | 0
In QA | 0
Blocked | 0
Not Started | 74
Deferred | 0
Priority | Open Count
P0 | 44
P1 | 15
P2 | 15
P3 | 0

## Lists (hidden)
Statuses | Priorities | Phases | Workstreams
Done | P0 | D0 | Strategy & Product Definition
In Progress | P1 | P0 | Research & Customer Discovery
In Review | P2 | P1 | UX, Design & Copy
In QA | P3 | P2 | Frontend Engineering
Blocked |  | P3 | Backend & Data Model
Not Started |  | P4 | Auth, Privacy & Trust
Deferred |  | P5 | WhatsApp & Messaging
|  | P6 | Analytics & Metrics
|  | P7 | Operator Setup & Support
Marketing, Sales & Launch
QA, Testing & Release Gates
Infrastructure & Deployment
AI & Learning Intelligence
Institution Expansion
Documentation & Handoff